## Sheet1
FUNDED AND INDICATIVE MEDIUM TERM PLAN FOR FLOOD RISK MANAGEMENT WALES CAPITAL PROGRAMME (2015/2016 ONWARDS)
APPROVED JANUARY 2016
PROJECT | LOCAL AUTHORITY | PROJECT TYPE | CONFIRMED FUNDING (£) | INDICATIVE FUNDING (£) | [8 empty] | TOTAL CONFIRMED AND INDICATIVE FUNDING (£) | PROJECT STAGE / ACTIVITY | [9 empty] | NUMBER OF HOUSEHOLDS WITH REDUCED FLOOD RISK | NUMBER OF BUSINESSES WITH REDUCED FLOOD RISK | NUMBER OF PROPERTIES ISSUED WITH INDIVIDUAL PROTECTION MEASURES | UK BIODIVERSITY ACTIONPLAN HABITAT CREATED (TERRESTRIAL) (Ha) | UK BIODIVERSITY ACTIONPLAN HABITAT CREATED (INTER-TIDAL) (Ha)
|  |  | 2017 - 2018 YR 0 (£) | 2018 - 2019 YR 1 (£) | 2019 - 2020 YR 2 (£) | 2020 - 2021 YR 3 (£) | 2021 - 2022 YR 4 (£) | 2022 - 2023 YR 5 (£) | 2023 - 2024 YR 6 (£) | 2024 - 2025 YR 7 (£) | 2025 - 2026 YR 8 (£) | 2026 ONWARDS YR 9+ (£) | 2017-18 TO 2026+ | 2017 - 2018 YR 0 (£) | 2018 - 2019 YR 1 (£) | 2019 - 2020 YR 2 (£) | 2020 - 2021 YR 3 (£) | 2021 - 2022 YR 4 (£) | 2022 - 2023 YR 5 (£) | 2023 - 2024 YR 6 (£) | 2024 - 2025 YR 7 (£) | 2025 - 2026 YR 8 (£) | 2026 ONWARDS YR 9+ (£) | 2017-18 TO 2026+ TOTAL | 2017-18 TO 2026+ TOTAL | 2017-18 TO 2026+ TOTAL | 2017-18 TO 2026+ TOTAL | 2017-18 TO 2026+ TOTAL
Aberbeeg Flow Monitoring Station | Blaenau Gwent - Blaenau Gwent | Maintenance | <5k | [9 empty] | <5k | Maintenance
Aberbeeg Woodland Wall Replacement | Blaenau Gwent - Blaenau Gwent | Maintenance | <5k | [9 empty] | <5k | Maintenance
Abertillery & Six Bells - Structural Assessment | Blaenau Gwent - Blaenau Gwent | Maintenance |  | <50k | <50k | [7 empty] | <100k |  | Study | Study
Abertillery/Six Bells Remedial Wall Repairs | Blaenau Gwent - Blaenau Gwent | Maintenance |  |  | <50k | [7 empty] | <50k |  |  | Maintenance
Pencoed Initial Assesment | Bridgend - Pen-yr-Bont ar Ogwr | Defence | <50k | <50k | [8 empty] | <50k | Study | Appraisal
Aberkenfig FAS | Bridgend - Pen-yr-Bont ar Ogwr | Defence | <50k | <100k | <100k | <500k | [6 empty] | <500k | Study | Appraisal | Design | Construction
River Ogmore Access Ladders | Bridgend - Pen-yr-Bont ar Ogwr | Maintenance | <5k | [9 empty] | <5k | Maintenance
Maesteg | Bridgend - Pen-yr-Bont ar Ogwr | Maintenance |  | <50k | <50k | <250k | [6 empty] | <250k |  | Design | Maintenance | Maintenance
Coychurch Natural Flood Management Techniques Trial | Bridgend - Pen-yr-Bont ar Ogwr | Other |  | <50k | [8 empty] | <50k |  | Study
Ogmore Vale Initial Assessment | Bridgend - Pen-yr-Bont ar Ogwr | Defence |  |  | <50k | <50k | <100k | <100k | <250k |  |  |  | <500k |  |  | Study | Appraisal | Design | Construction | Construction
Bridgend Maintenance | Bridgend - Pen-yr-Bont ar Ogwr | Maintenance
Coytrahen Station Refurbishment | Bridgend - Pen-yr-Bont ar Ogwr | Maintenance
Keepers Lodge Ramp | Bridgend - Pen-yr-Bont ar Ogwr | Maintenance
Nant Brynglas Trash Screen | Bridgend - Pen-yr-Bont ar Ogwr | Maintenance
Risca Flood Risk Management | Caerphilly - Caerffili | Defence | <50k | <5k | <5k | <5k | <5k | [5 empty] | <50k | Construction | Completion | Completion | Completion | Completion | [5 empty] | 259 | 19
Bridge St, Newbridge - New FAS | Caerphilly - Caerffili | Defence |  | <100k | <100k | [7 empty] | <250k |  | Appraisal | Design
Llanbradach - New Embankment | Caerphilly - Caerffili | Defence |  | <100k | [8 empty] | <100k |  | Construction
Machen Initial Assessment | Caerphilly - Caerffili | Defence |  | <50k | [8 empty] | <50k |  | Study
Caerphilly Tributaires | Caerphilly - Caerffili | Maintenance |  |  | <50k | [7 empty] | <50k |  |  | Maintenance
Ystrad Mynach Deshoal | Caerphilly - Caerffili | Maintenance |  |  |  |  | <50k | [5 empty] | <50k |  |  |  |  | Maintenance
Coedypia, Ystrad Mynach - Structural Assessment | Caerphilly - Caerffili | Maintenance |  |  | <50k | [7 empty] | <50k |  |  | Study
Bedwas Walls - Structural Assessment | Caerphilly - Caerffili | Maintenance |  |  | <50k | [7 empty] | <50k |  |  | Study
New Tredegar Deshoal | Caerphilly - Caerffili | Maintenance |  |  |  |  | <50k | [5 empty] | <50k |  |  |  |  | Maintenance
Dyffryn Meadows Ind Est - Improve FAS | Caerphilly - Caerffili | Maintenance |  |  |  |  | <100k | <1000k |  |  |  |  | <1000k |  |  |  |  | Design | Maintenance
Ystrad Mynach Deshoal and Embankment Repairs | Caerphilly - Caerffili | Maintenance
Bedwas House Embankment | Caerphilly - Caerffili | Maintenance
Leckwith Bridge Industrial Estate | Cardiff - Caerdydd | Maintenance | <250k | <250k | [8 empty] | <500k | Maintenance | Maintenance
Cardiff Bay Siltation Monitoring | Cardiff - Caerdydd | Maintenance | <50k | [9 empty] | <50k | Maintenance
Roath and Rhymney Flood Risk Management | Cardiff - Caerdydd | Defence | <5000k | <2500k | <250k | <50k | [6 empty] | >5000k | Construction | Construction | Construction | Completion | [6 empty] | 360 | 51
Cardiff Remedial Wall Repairs (Ops Delivery) | Cardiff - Caerdydd | Maintenance |  | <50k | [8 empty] | <50k |  | Maintenance
Melingriffith - Bank Repairs | Cardiff - Caerdydd | Maintenance |  | <50k | [8 empty] | <50k |  | Maintenance
Cardiff FAS - Scheme Review | Cardiff - Caerdydd | Defence |  |  | <250k | [6 empty] | >5000k | >5000k |  |  | Appraisal | [6 empty] | Construction
Cardiff Embankment Repairs (Ops Delivery) | Cardiff - Caerdydd | Maintenance |  |  | <50k | [7 empty] | <50k |  |  | Maintenance
Began Farm Blockstone Repairs | Cardiff - Caerdydd | Maintenance |  |  |  | <50k | [6 empty] | <50k |  |  |  | Maintenance
Ball Road, Llanrumney | Cardiff - Caerdydd | Maintenance |  |  | <50k | [7 empty] | <50k |  |  | Maintenance
Llanrumney - Retreat of Defences | Cardiff - Caerdydd | Maintenance |  |  |  |  | <500k | [5 empty] | <500k |  |  |  |  | Construction
Broadway Reen Tipping Weir | Cardiff - Caerdydd | Maintenance
Tongwynlais FW Station Refurbishment | Cardiff - Caerdydd | Maintenance
Machynys Flood Defence Maintenance | Carmarthenshire - Sir Gaerfyrddin | Maintenance | <1000k | <500k | [8 empty] | <2500k | Maintenance | Maintenance
Pwll Flood Risk Management | Carmarthenshire - Sir Gaerfyrddin | Defence | <50k | [9 empty] | <50k | Maintenance | [9 empty] | 153 | 5
Pendine Sluice and Gate Refurbishment | Carmarthenshire - Sir Gaerfyrddin | Maintenance | <5k | [9 empty] | <5k | Maintenance
Pontyates Floodbank | Carmarthenshire - Sir Gaerfyrddin | Maintenance | <5k | [9 empty] | <5k | Maintenance
Tywi Access Improvements | Carmarthenshire - Sir Gaerfyrddin | Maintenance | <50k | [9 empty] | <50k | Maintenance
Dafen Vegitation Clearance | Carmarthenshire - Sir Gaerfyrddin | Maintenance | <50k | [9 empty] | <50k | Maintenance
North Dafen Attenuation Pond | Carmarthenshire - Sir Gaerfyrddin | Defence | <50k | <1000k | <1000K | <500k | [6 empty] | <2500k | Design | Construction | Construction | Construction
Carmarthen Topographic Survey - Phase 1 | Carmarthenshire - Sir Gaerfyrddin | Modelling | <50k | [9 empty] | <50k | Design
Ammanford FAS | Carmarthenshire - Sir Gaerfyrddin | Defence | <50k | <500k | <1000K | <2500k | <1000k | [5 empty] | <2500k | Appraisal | Design | Construction | Construction | Construction | [5 empty] | TBC | TBC
Llandovery Wall and Bank Improvements | Carmarthenshire - Sir Gaerfyrddin | Maintenance |  | <50k | [8 empty] | <50k |  | Maintenance
Laugharne Mill Leat De Silt | Carmarthenshire - Sir Gaerfyrddin | Maintenance |  | <50k | [8 empty] | <50k |  | Maintenance
Llandovery | Carmarthenshire - Sir Gaerfyrddin | Maintenance |  | <50k | [8 empty] | <50k |  | Maintenance
Dafen Gabion Repair | Carmarthenshire - Sir Gaerfyrddin | Maintenance |  | <50k | [8 empty] | <50k |  | Maintenance
Johnstown FAS | Carmarthenshire - Sir Gaerfyrddin | Defence |  | <50k | <50k | [7 empty] | <50k |  | Study | Appraisal
Mwche Managed Realignment | Carmarthenshire - Sir Gaerfyrddin | Biodiversity and Habitat Enhancement | [25 empty] | TBC
Trothy Catchment Habitat Creation Project | Carmarthenshire - Sir Gaerfyrddin | Biodiversity and Habitat Enhancement | [24 empty] | 5
Llanybydder FAS | Carmarthenshire - Sir Gaerfyrddin | Defence |  |  |  |  | <50k | <50k | <250k |  |  |  | <250k |  |  |  |  | Appraisal | Design | Construction
Clog y Fran Bank Improvements | Carmarthenshire - Sir Gaerfyrddin | Maintenance
Llandovery Gravel Management 16/17 | Carmarthenshire - Sir Gaerfyrddin | Maintenance
Llanwrda Wall | Carmarthenshire - Sir Gaerfyrddin | Maintenance
Lliedi Blockstone Repairs | Carmarthenshire - Sir Gaerfyrddin | Maintenance
Pendine Access Track | Carmarthenshire - Sir Gaerfyrddin | Maintenance
Pwll FAS - Underpin Wall | Carmarthenshire - Sir Gaerfyrddin | Maintenance
Whitland Coping Stone Replacement | Carmarthenshire - Sir Gaerfyrddin | Maintenance
Whitland Flood Defence Underpinning | Carmarthenshire - Sir Gaerfyrddin | Maintenance
Abergwili Access Improvements | Carmarthenshire - Sir Gaerfyrddin | Maintenance
Hendy Flood Risk Mapping Study | Carmarthenshire - Sir Gaerfyrddin | Modelling
Cardigan Tidal Defences | Ceredigion - Sir Ceredigion | Defence | <5k |  | <1000K | <1000k | <5000k | <2500k | <2500k |  |  |  | >5000k | Study |  | Appraisal | Design | Construction | Construction | Construction |  |  |  | TBC | TBC
Aberystwyth Wall | Ceredigion - Sir Ceredigion | Maintenance | <50k | [9 empty] | <50k | Maintenance
Cwmystwyth Station & Weir Refurbishment | Ceredigion - Sir Ceredigion | Maintenance | <50k | [9 empty] | <50k | Maintenance
Ffos Glanwern Timber Revetment Repairs | Ceredigion - Sir Ceredigion | Maintenance | <50k | [9 empty] | <50k | Maintenance
Parc yr Onnen | Ceredigion - Sir Ceredigion | Defence | <100k | <100k | [8 empty] | <250k | Design | Construction
Borth Modelling | Ceredigion - Sir Ceredigion | Modelling |  | <50k | <50k | <100k |  |  |  | <2500k |  |  | <2500k |  | Design | Construction | Construction |  |  |  | Construction
Aberystwyth Initial Assessment | Ceredigion - Sir Ceredigion | Defence |  | <50k | <100k | <1000k | <2500K | <2500k |  |  |  |  | <5000k |  | Study | Appraisal | Design | Construction | Construction
Teifi Headwaters Wetland Creation and Peat Restoration | Ceredigion - Sir Ceredigion | Biodiversity and Habitat Enhancement | [24 empty] | 20
Tregaron Flood Risk Management | Ceredigion - Sir Ceredigion | Defence
Lampeter Initial Assessment | Ceredigion - Sir Ceredigion | Defence |  |  | <50k | <50k | <500k | [5 empty] | <500k |  |  | Appraisal | Design | Construction
Aberaeron | Ceredigion - Sir Ceredigion | Maintenance |  |  | <50k | [7 empty] | <50k |  |  | Maintenance
Glanwern Chamber and Outfall Repairs | Ceredigion - Sir Ceredigion | Maintenance
Llanrhystud Ford | Ceredigion - Sir Ceredigion | Maintenance
Lampeter and Llanybydder Mapping Study | Ceredigion - Sir Ceredigion | Modelling
Pentre Cwrt and Llandysul Mapping Study | Ceredigion - Sir Ceredigion | Modelling
Tanlan Embankment Viablity Study | Conwy - Conwy | Maintenance | <50k | <50k | [8 empty] | <50k | Other | Other
White Barn North - Culvert Replacement | Conwy - Conwy | Maintenance | <100k | <100k | [8 empty] | <250k | Maintenance | Maintenance
Afon Conwy Tan Lan Breach Repair | Conwy - Conwy | Maintenance | <100k | [9 empty] | <100k | Maintenance
Afon Wydden Spillway Works | Conwy - Conwy | Maintenance | <250k | [9 empty] | <250k | Maintenance
Llanfair Talhaiarn Phase 3 | Conwy - Conwy | Defence | <250k | <1000k | <50k | [7 empty] | <1000k | Design | Construction | Completion
Dyffryn Conwy Flood Risk Management | Conwy - Conwy | Defence | <50k | [9 empty] | <50k | Completion
Gele Sluice | Conwy - Conwy | Maintenance | <50k | <250k | <1000K | <1000k | <5k | [5 empty] | <2500k | Appraisal | Design | Construction | Construction | Completion
Morfa Madryn Compensation Habitat Creation | Conwy - Conwy | Biodiversity and Habitat Enhancement | <5k | [9 empty] | <5k | Appraisal | [13 empty] | TBC
Trefriw -Stone Frontage Repair | Conwy - Conwy | Maintenance |  | <50k | [8 empty] | <50k |  | Maintenance
Llandudno (incl Penrhyn Bay and Rhos On Sea) - Tidal Flood Risk Modelling | Conwy - Conwy | Modelling |  | <100k | [8 empty] | <100k |  | Maintenance
Mochdre Initial Assessment | Conwy - Conwy | Defence |  | <50k | [8 empty] | <50k |  | Study
Llanfair TH-Nant Barrog Phase 2 | Conwy - Conwy | Defence
Llanrwst Gravel Management 16/17 | Conwy - Conwy | Maintenance
Afon Wydden Flood Risk Mapping Study | Conwy - Conwy | Modelling
Conwy Valley Phase 3 | Conwy - Conwy | Modelling
Rhyl and Prestatyn Tidal Flood Risk Study | Denbighshire - Sir Ddinbych | Modelling | <50k | [9 empty] | <50k | Study
Rhyl and Prestatyn Fluvial Modelling Study | Denbighshire - Sir Ddinbych | Modelling | <50k | [9 empty] | <50k | Study
River Elwy Erosion Repairs | Denbighshire - Sir Ddinbych | Maintenance | <50k | [9 empty] | <50k | Maintenance
Rhyl Cut Access Improvements | Denbighshire - Sir Ddinbych | Maintenance | <50k | [9 empty] | <50k | Maintenance
Warren Drive Trash screen | Denbighshire - Sir Ddinbych | Maintenance | <50k | [9 empty] | <50k | Maintenance
Rhyl Sluice | Denbighshire - Sir Ddinbych | Maintenance | <50k | [9 empty] | <50k | Maintenance
Tidal Clwyd FRMS Review 2017 | Denbighshire - Sir Ddinbych | Modelling | <50k | [9 empty] | <50k | Maintenance
Glanfyddion Sluice | Denbighshire - Sir Ddinbych | Maintenance | <250k | <1000k | <5k | [7 empty] | <1000k | Design | Construction | Completion
Rhyl Cut & Prestatyn Gutter Fluvial Modelling | Denbighshire - Sir Ddinbych | Modelling | <50k | <50k | [8 empty] | <100k | Design | Construction
Pont Robin Tidal Outfall Refurbishment | Denbighshire - Sir Ddinbych | Maintenance | <100k | <500k | <5k | [7 empty] | <500k | Design | Maintenance | Maintenance
St Asaph FCRM | Denbighshire - Sir Ddinbych | Defence | <5000k | <250k | <50k | <5k | <5k | <5k |  |  |  |  | <5000k | Construction | Construction | Completion | Completion | Completion | Completion |  |  |  |  | 510 | 38
Dyserth | Denbighshire - Sir Ddinbych | Maintenance |  | <50k |  |  |  | <100k | <2500k |  |  |  | <2500k |  | Appraisal |  |  |  | Design | Construction
Abergele Bypass Culvert | Denbighshire - Sir Ddinbych | Maintenance |  | <50k | [8 empty] | <50k |  | Maintenance
Ffynnon y Ddol Culvert Works | Denbighshire - Sir Ddinbych | Maintenance |  | <50k | [8 empty] | <50k |  | Maintenance
Elwy - Retreat Flood Embankment | Denbighshire - Sir Ddinbych | Maintenance |  | <50k | [8 empty] | <50k |  | Maintenance
Work arising from the Clwyd strategy | Denbighshire - Sir Ddinbych | Defence |  | <250k | <250k | <1000k | <1000k | <2500k | <2500k | <2500k | <5000k | >5000k | >5000k |  | Other | Other | Other | Other | Other | Other | Other | Other | Other
Rhyl & Gronannt Pump Station Review | Denbighshire - Sir Ddinbych | Other |  | <50k | <50k | <50k | <50k | [5 empty] | <50k |  | Study | Study | Appraisal | Other
Belgrano & Clwyd Pump Station Review | Denbighshire - Sir Ddinbych | Other |  | <50k | <50k | <50k | <50k | <50k | <250k |  |  |  | <250k |  | Study | Study | Appraisal | Other | Other | Other
Bodoryn & Gypsey Lane Pump Station Review | Denbighshire - Sir Ddinbych | Other |  | <50k | <50k | <50k | <50k | <50k | <250k |  |  |  | <250k |  | Study | Study | Appraisal | Other | Other | Other
Maes Maelor Bog Creation | Denbighshire - Sir Ddinbych | Biodiversity and Habitat Enhancement | [24 empty] | 9
Dee - Tidal Structure Assessments | Denbighshire - Sir Ddinbych | Maintenance |  |  | <50k | <250k | <500k | <500k |  |  |  |  | <1000k |  |  | Appraisal | Design | Construction | Construction
Cae Rau Cottage Embankment Refurbishment | Denbighshire - Sir Ddinbych | Maintenance
Marine Lake Embankment | Denbighshire - Sir Ddinbych | Maintenance
NE Wales Trash Screen Designs | Denbighshire - Sir Ddinbych | Maintenance
St Asaph Phase 3 Works City Bridge to Elwy Weir | Denbighshire - Sir Ddinbych | Maintenance
Sun Valley Embankment Refurbishment | Denbighshire - Sir Ddinbych | Maintenance
Dee Embankment H+S Improvement Works | Flintshire - Sir y Fflint | Maintenance | <50k | [9 empty] | <50k | Maintenance
Rowleys Pumping Station Weedscreen | Flintshire - Sir y Fflint | Maintenance | <50k | [9 empty] | <50k | Maintenance
Point of Ayr | Flintshire - Sir y Fflint | Maintenance | <50k | <250k | <500k | <5k | [6 empty] | <1000k | Appraisal | Design | Construction | Completion
Thornleigh PS Bank Stabalisation | Flintshire - Sir y Fflint | Maintenance |  | <50k | [8 empty] | <50k |  | Maintenance
Beeches Drain Outfall | Flintshire - Sir y Fflint | Maintenance |  | <50k | <100k | [7 empty] | <100k |  | Maintenance | Maintenance
Sealand - Northern Embankment Slump | Flintshire - Sir y Fflint | Maintenance |  | <50k | <250k | [7 empty] | <250k |  | Maintenance | Maintenance
Wepre Gutter Pilling Works | Flintshire - Sir y Fflint | Maintenance |  | <250k | [8 empty] | <250k |  | Maintenance | Maintenance
Work arising from the Dee strategy | Flintshire - Sir y Fflint | Defence |  | <250k | <250k | <1000k | <1000k | <1000k | <2500k | <5000k | <2500k | >5000k | >5000k |  | Other | Other | Other | Other | Other | Other | Other | Other | Other
Talacre Pumping Station Efficiency Improvements | Flintshire - Sir y Fflint | Maintenance |  | <50k | <50k | <50k | <100k | [5 empty] | <100k |  | Other | Other | Other | Other
Bretten Initial Assessment | Flintshire - Sir y Fflint | Defence |  | <50k | [8 empty] | <50k |  | Study
Wepre Initial Assessment | Flintshire - Sir y Fflint | Defence |  | <50k | <100k | [7 empty] | <100k |  | Study | Appraisal
Balderton Pump Station Review | Flintshire - Sir y Fflint | Other |  | <50k | <50k | <50k | <250k | [5 empty] | <250k |  | Study | Study | Appraisal | Other
Sealand & Thornleigh Pump Station Review | Flintshire - Sir y Fflint | Other |  | <50k | <50k | <50k | <50k | <250k |  |  |  |  | <250k |  | Study | Study | Appraisal | Other | Other
Higherferry Queensferry & Rowleys Pump Station Review | Flintshire - Sir y Fflint | Other |  | <50k | <50k | <50k | <250k | [5 empty] | <250k |  | Study | Study | Appraisal | Other
Pontblyddyn project | Flintshire - Sir y Fflint | Defence
Greenfield Embankment Improvements | Flintshire - Sir y Fflint | Maintenance | [6 empty] | <100k | <100k | <2500k |  | <2500k | [6 empty] | Design | Construction | Construction
Bagillt Telemetry Installation | Flintshire - Sir y Fflint | Maintenance
Sandycroft Penstock Door Insullation | Flintshire - Sir y Fflint | Maintenance
Garndolbenmaen Gauging Station | Gwynedd - Gwynedd | Maintenance | <50k | <5k | [8 empty] | <50k | Maintenance | Maintenance
Vale of Ffestiniog Land Purchase | Gwynedd - Gwynedd | Biodiversity and Habitat Enhancement | <5k | [9 empty] | <5k | Maintenance
Ty Gwyn Tidal doors and penstock renewal | Gwynedd - Gwynedd | Maintenance | <50k | [9 empty] | <50k | Maintenance
Draenogau Tidal Doors | Gwynedd - Gwynedd | Maintenance | <50k | [9 empty] | <50k | Maintenance
Harlech Weedscreens | Gwynedd - Gwynedd | Maintenance | <50k | [9 empty] | <50k | Maintenance
Llyn Tegid Section 10 Repairs | Gwynedd - Gwynedd | Maintenance | <50k | [9 empty] | <50k | Maintenance
Llyn Tegid PLC's | Gwynedd - Gwynedd | Maintenance | <50k | [9 empty] | <50k | Maintenance
Glaslyn Tidal Doors - Emergency Works | Gwynedd - Gwynedd | Maintenance | <250k | [9 empty] | <250k | Maintenance
Dysynni Low Level Outfall Tidal Doors Replacement | Gwynedd - Gwynedd | Maintenance | <250k | [9 empty] | <250k | Maintenance
Porthmadog Tidal Structures | Gwynedd - Gwynedd | Defence | <100k | <250k | <50k | <50k | <50k | <50k | <100k |  |  |  | <500k | Design | Construction | Construction | Completion | Completion | Completion | Completion
Ffriog Cliffs Sea Defence Repairs | Gwynedd - Gwynedd | Maintenance | <500k | <1000k | [8 empty] | <2500k | Design | Construction
Llyn Tegid Reservoir Safety Works | Gwynedd - Gwynedd | Maintenance | <250k | <250k | <5000k | <2500k | <1000k | [5 empty] | >5000k | Design | Design | Construction | Construction | Construction
Cynefail Gauging Station | Gwynedd - Gwynedd | Maintenance | <5k | [9 empty] | <5k | Construction
Dolgellau (Wnion and Arran) Flood Risk Management | Gwynedd - Gwynedd | Defence | <250k | <5k | <5k | <5k | <50k | [5 empty] | <250k | Completion | Completion | Completion | Completion | Completion | [5 empty] | 182 | 128
Fairbourne Flood Risk Management Scheme | Gwynedd - Gwynedd | Defence | <250k | [9 empty] | <250k | Completion | [9 empty] | 410 | 10
Porthmadog Fluvial Options Appraisal | Gwynedd - Gwynedd | Defence | <50k | <50k | <50k | <250k | <2500K | <5000k |  |  |  |  | <5000k | Appraisal | Design | Design | Construction | Construction | Construction
Vale of Ffestiniog Compensation Habitat Creation | Gwynedd - Gwynedd | Biodiversity and Habitat Enhancement | <5k | [9 empty] | <5k | Appraisal | [13 empty] | TBC
Penllyn Tywyn Outfall | Gwynedd - Gwynedd | Maintenance |  | <50k | [8 empty] | <50k |  | Maintenance
CWRT Chamber & Weedscreen | Gwynedd - Gwynedd | Maintenance |  | <50k | [8 empty] | <50k |  | Maintenance
Llandanwg Breakwater | Gwynedd - Gwynedd | Maintenance |  | <50k | [8 empty] | <50k |  | Maintenance
Aberech Bank Reprofile | Gwynedd - Gwynedd | Maintenance |  | <250k | [8 empty] | <250k |  | Maintenance
Mochras Flood Bank and Tidal Door | Gwynedd - Gwynedd | Maintenance |  | <50k | <50k | [6 empty] | <5000k | <5000k |  | Maintenance | Maintenance | [6 empty] | Maintenance
Ty Gwyn Tidal Door Modelling | Gwynedd - Gwynedd | Modelling |  | <50k | <50k | [6 empty] | <5000k | <5000k |  | Maintenance | Maintenance | [6 empty] | Construction
Tidal Dyfi Strategy | Gwynedd - Gwynedd | Defence |  | <50k | <50k | [7 empty] | <50k |  | Study | Study
Dinas Dinlle Strategy | Gwynedd - Gwynedd | Other |  | <50k | <100k | <100k | <1000k | <1000k |  |  |  |  | <2500k |  | Study | Study | Appraisal | Other | Other
Llechwedd Llwyd Phase III | Gwynedd - Gwynedd | Biodiversity and Habitat Enhancement | [24 empty] | 22
Morfa Madryn Coastal Realignment | Gwynedd - Gwynedd | Biodiversity and Habitat Enhancement | [25 empty] | TBC
Ty Uchaf - Cors y Sarnau Wetland Project | Gwynedd - Gwynedd | Biodiversity and Habitat Enhancement | [24 empty] | 19
Porthmadog Flood Risk Management | Gwynedd - Gwynedd | Defence
Afon Rhyd Hir | Gwynedd - Gwynedd | Defence | [6 empty] | <250k | <2500k |  |  | <2500k | [6 empty] | Design | Construction
Fairbourne & Barmouth - Tidal Flood Risk Modelling | Gwynedd - Gwynedd | Modelling |  |  | <100k | [7 empty] | <100k |  |  | Construction
Aberdesach Flood Improvement Works | Gwynedd - Gwynedd | Maintenance
Afon Adda Culvert Clearance | Gwynedd - Gwynedd | Maintenance
Corwen Roof Repairs | Gwynedd - Gwynedd | Maintenance
Friog Corner Emergency Works 2016 | Gwynedd - Gwynedd | Maintenance
Llyn Tegid - Main Gate Maintenance | Gwynedd - Gwynedd | Maintenance
Llyn Tegid Gravel Removal | Gwynedd - Gwynedd | Maintenance
Llyn Tegid Section 10 Improvement Works | Gwynedd - Gwynedd | Maintenance
Llyn Tegid Sluice - Fish Migration Investigation | Gwynedd - Gwynedd | Maintenance
Mochras Tidal Door Replacement | Gwynedd - Gwynedd | Maintenance
Llanddulas and Bontnewydd Flood Analysis and Modelling | Gwynedd - Gwynedd | Modelling
Mawddach Modelling | Gwynedd - Gwynedd | Modelling
Malltraeth Tidal Doors Replacement | Isle of Anglesey - Sir Ynys Mon | Maintenance | <100k | [9 empty] | <100k | Maintenance
Amlwch | Isle of Anglesey - Sir Ynys Mon | Maintenance |  | <100k | <1000K | [7 empty] | <1000k |  | Appraisal | Maintenance
Valley | Isle of Anglesey - Sir Ynys Mon | Maintenance |  | <50k | [5 empty] | <250k | <2500k | <2500k | <2500k |  | Maintenance | [5 empty] | Design | Maintenance | Maintenance
Troedyrhiw - New FAS [RB] | Merthyr Tydfil - Merthyr Tudful | Defence | [9 empty] | <2500k | <2500k | [9 empty] | Construction
Chepstow FAS - Gate Replacement | Monmouthshire - Sir Fynwy | Maintenance | <50k | <5k | [8 empty] | <50k | Maintenance | Maintenance
Julians Reen Access Improvements and Wing Wall Repair | Monmouthshire - Sir Fynwy | Maintenance | <50k | <50k | [8 empty] | <100k | Maintenance | Maintenance
Selwyns Door - Culvert Replacement | Monmouthshire - Sir Fynwy | Maintenance | <50k | <50k | [8 empty] | <100k | Maintenance | Maintenance
Redbrook Gauging Station Refurbishment | Monmouthshire - Sir Fynwy | Maintenance | <5k | [9 empty] | <5k | Maintenance
West Pill Outfall Improvments | Monmouthshire - Sir Fynwy | Maintenance | <50k | [9 empty] | <50k | Maintenance
St Regis Sea Defence Repair | Monmouthshire - Sir Fynwy | Maintenance | <50k | [9 empty] | <50k | Maintenance
Sea Doors - Asset Replacement Study | Monmouthshire - Sir Fynwy | Maintenance | <50k | [9 empty] | <50k | Maintenance
Portland Grounds Sea Defence Improvement | Monmouthshire - Sir Fynwy | Defence | <50k | [9 empty] | <50k | Completion | [9 empty] | 263 | 17
Monmouth Flood Gates - Improvements | Monmouthshire - Sir Fynwy | Maintenance |  | <100k | [8 empty] | <100k |  | Maintenance
Monmouth - River Wye Left Bank | Monmouthshire - Sir Fynwy | Maintenance |  |  | <50k | <250k | [6 empty] | <250k |  |  | Design | Maintenance
Sudbrook/Chepstow - Sea Defence Improvements | Monmouthshire - Sir Fynwy | Maintenance | [6 empty] | <500k | <2500k |  |  | <2500k | [6 empty] | Design | Maintenance
Greenmoor Pumping Station | Monmouthshire - Sir Fynwy | Maintenance
Port Talbot Gravel Removal | Neath Port Talbot - Castell-nedd Port Talbot | Maintenance | <50k | <50k | [8 empty] | <50k | Maintenance | Maintenance
Crynant Post Event Remedial Work | Neath Port Talbot - Castell-nedd Port Talbot | Maintenance | <50k | <50k | [8 empty] | <50k | Maintenance | Maintenance
Cwmgwrach Gabion Repairs and Channel Improvements | Neath Port Talbot - Castell-nedd Port Talbot | Maintenance | <50k | [9 empty] | <50k | Maintenance
Cwm Clydach Dam Repairs | Neath Port Talbot - Castell-nedd Port Talbot | Maintenance | <250k | [9 empty] | <250k | Maintenance
Resolven Weir Refurbishment | Neath Port Talbot - Castell-nedd Port Talbot | Maintenance | <100k | <5k | [8 empty] | <100k | Construction | Completion
Cilfrew Weir Refurbishment | Neath Port Talbot - Castell-nedd Port Talbot | Maintenance | <250k | <5k | [8 empty] | <250k | Construction | Completion
Resolven FAS Mitigation Site | Neath Port Talbot - Castell-nedd Port Talbot | Biodiversity and Habitat Enhancement | <50k | [9 empty] | <50k | Construction | [12 empty] | 5
Ffrwd Wyllt Fluvial Initial Assessment | Neath Port Talbot - Castell-nedd Port Talbot | Defence | <50k |  |  |  | <250k | <500k | <2500k |  |  |  | <2500k | Completion |  |  |  | Design | Construction | Construction
Margam | Neath Port Talbot - Castell-nedd Port Talbot | Defence |  | <50k | <250k | <250k | [6 empty] | <500k |  | Appraisal | Design | Construction
Cadoxton Neath Initial Assessment | Neath Port Talbot - Castell-nedd Port Talbot | Defence | [6 empty] | <50k | <250k | <250k |  | <500k | [6 empty] | Appraisal | Design | Construction
Cwmafan Initial Assessment | Neath Port Talbot - Castell-nedd Port Talbot | Defence |  |  |  | <50k | <250k | <250k |  |  |  |  | <500k |  |  |  | Study | Appraisal | Design
Marcroft Public Safety Improvements | Neath Port Talbot - Castell-nedd Port Talbot | Maintenance
Clydach Flood Risk Mapping Study | Neath Port Talbot - Castell-nedd Port Talbot | Modelling
Crynant Flood Risk Mapping Study | Neath Port Talbot - Castell-nedd Port Talbot | Modelling
Crindau Pill Flood Risk Management Improvements | Newport - Casnewydd | Defence | >5000k | <2500k | <500k | <50k | <50k | <5k |  |  |  |  | >5000k | Construction | Construction | Construction | Construction | Completion | Completion |  |  |  |  | 549 | 118
Isca Road - Wall Repair | Newport - Casnewydd | Maintenance | <50k | [9 empty] | <50k | Construction | [9 empty] | 49 | 1
Riverside Newport Flood Risk Management | Newport - Casnewydd | Defence | <5k | [10 empty] | Completion | [9 empty] | 373 | 47
Tabbs Gout Sea Defence Improvements | Newport - Casnewydd | Defence | <50k | [9 empty] | <50k | Completion | [9 empty] | 570 | 180
Stephenson Street, Liswerry | Newport - Casnewydd | Maintenance | <5k | [9 empty] | <5k | Completion | [9 empty] | TBC | TBC
Tarwick Reen - Sluice Replacement | Newport - Casnewydd | Maintenance |  | <50k | [8 empty] | <50k |  | Maintenance
Home Farm, Caerleon - New FAS | Newport - Casnewydd | Defence |  |  |  | <100k | [6 empty] | <100k |  |  |  | Appraisal
Liswerry Pill - New FAS | Newport - Casnewydd | Defence |  |  |  |  | <50k | <250k | <2500k | <2500k |  |  | <2500k |  |  |  |  | Appraisal | Design | Construction | Construction
Back Ditch | Newport - Casnewydd | Maintenance |  |  | <50k | [7 empty] | <50k |  |  | Maintenance
Tredegar Park Shoal Removal | Newport - Casnewydd | Maintenance |  |  |  |  | <50k | [5 empty] | <50k |  |  |  |  | Maintenance
Riverside Newport - 90s Wall [Structural Assessment] | Newport - Casnewydd | Maintenance |  |  | <50k | [7 empty] | <50k |  |  | Maintenance
Chapel Reen Sea Door Replacement | Newport - Casnewydd | Maintenance
Docksway Embankment and Deshoal | Newport - Casnewydd | Maintenance
Monks Ditch Sea Door Replacement | Newport - Casnewydd | Maintenance
Undy Pumping Station Revetment Repairs | Newport - Casnewydd | Maintenance
Northern Area Pumping Station Review | Other | Other | <50k | <100k | [8 empty] | <100k | Study | Study
NHCP Projects | Other | Biodiversity and Habitat Enhancement | <1000k | <2500k | <2500k | <2500k | <2500K | <2500k | <2500k | <2500k | <2500k | <5000k | >5000k | Other | Other | Other | Other | Other | Other | Other | Other | Other | Other
FRM Transformation - Software Purchases | Other | ICT | <5k | <50k | [8 empty] | <50k | Other | Other
Replacement Flood Risk Asset Management System | Other | ICT | <100k | <100k | [8 empty] | <250k | Other | Other
Telemetry Wales 2020 (Telemetry Strategy) | Other | ICT | <250k | <500k | <500k | <500k | [6 empty] | <2500k | Other | Other | Other | Other
Landscape Maintenance | Other | Maintenance | <50k | <50k | <5k | <50k | [6 empty] | <100k | Other | Other | Other | Other
Wales FRM Capital Sals (EAW) | Other | Other | <2500k | <2500k | <2500k | <2500k | <2500K | <2500k | <2500k | <2500k | <2500k | <5000k | >5000k | Other | Other | Other | Other | Other | Other | Other | Other | Other | Other
Transport and Plant Hydrometry (Contribution) | Other | Vehicles | <50k | <50k | <50k | <50k | <50k | <50k | <50k | <50k | <50k | <100k | <500k | Other | Other | Other | Other | Other | Other | Other | Other | Other | Other
Wales FCRM Fleet Asset Replacement Programme | Other | Vehicles | <1000k | <1000k | <1000K | <1000k | <1000k | <1000k | <1000k | <1000k | <1000k | <2500k | >5000k | Other | Other | Other | Other | Other | Other | Other | Other | Other | Other
NRW PPMTs | Other | ICT | <50k | [9 empty] | <50k | Other
FRM Transformation - NaFRA Replacement Product | Other | ICT | <500k | [9 empty] | <500k | Other
FRM Transformation | Other | ICT | <2500k | [9 empty] | <2500k | Other
River Ebbw Integrated Catchment Model | Other | Modelling | <5k | [9 empty] | <5k | Other
Wales FCRM Fleet Asset Replacement Programme 16/17 | Other | Vehicles | <1000k | [9 empty] | <1000k | Other
Culvert CCTV Survey Programme | Other | Maintenance | <50k | <50k | [5 empty] | <50k | <50k | <50k | <100k | Maintenance | Maintenance | [5 empty] | Maintenance | Maintenance | Maintenance
MEICA Asset Management Systems | Other | Maintenance | <50k | <100k | <100k | <100k | <100k | <100k | <100k | <100k | <100k | <250k | <1000k | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance
Flood Forecasting Hydrometric Improvements | Other | Modelling | <100k | <100k | <100k | <100k | <100k | <100k | <100k | <100k | <100k | <250k | <1000k | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance
SW Access Areas | Other | Maintenance | <5k | [9 empty] | <5k | Maintenance
Coastal Outfall Maintenance Appraisal (SW ASM) | Other | Maintenance | <50k | [9 empty] | <50k | Maintenance
CCTV Culvert Surveys SW | Other | Maintenance | <50k | [9 empty] | <50k | Maintenance
Northern Area Pumping Station Review - Phase 4A | Other | Maintenance | <50k | [9 empty] | <50k | Maintenance
FRA Scoping Assessment and Model Validation | Other | Modelling | <50k | [9 empty] | <50k | Maintenance
NE Wales Tidal Defences Survey | Other | Modelling | <5k | <5k | <5k | <5k | [6 empty] | <50k | Appraisal | Appraisal | Appraisal | Appraisal
Ladder Replacement Programme | Other | Maintenance |  | <100k | [8 empty] | <100k |  | Maintenance
Culverts Moving Forward Project | Other | Maintenance |  | <50k | <50k | <50k | [6 empty] | <100k |  | Maintenance | Maintenance | Maintenance
South East Area Mapping Projects | Other | Modelling |  | <250k | <250k | <250k | <250k | <250k | <250k | <250k | <250k | <250k | <2500k |  | Other | Other | Other | Other | Other | Other | Other | Other | Other
South West Area Mapping projects | Other | Modelling |  | <250k | <250k | <250k | <250k | <250k | <250k | <250k | <250k | <250k | <2500k |  | Other | Other | Other | Other | Other | Other | Other | Other | Other
Northern Area Mapping | Other | Modelling |  | <250k | <250k | <250k | <250k | <250k | <250k | <250k | <250k | <250k | <2500k |  | Other | Other | Other | Other | Other | Other | Other | Other | Other
IDD / FRM asset withdrawal review | Other | Other |  | <100k | <100k | [7 empty] | <250k |  | Study | Study
NHCP Land Investigations and Feasibility | Other | Biodiversity and Habitat Enhancement
FRM Transformation - Flood Warnings Online | Other | ICT
FRM Transformation - FWD Replacement | Other | ICT
FRM Transformation - ICT Project Staff | Other | ICT
FRM Transformation - NFFS Replacement | Other | ICT
FRM Transformation - Software Support and Maintenance | Other | ICT
FRM Transformation - Strategic Modelling Platform | Other | ICT
Public Safety Improvements 2016-17 | Other | Maintenance
ARC LITE Remote Control Boat | Other | Maintenance
North Area High Consequence Assets - Culvert Inspections | Other | Maintenance
North Wales Culvert Inspection and Maintenance | Other | Maintenance
Remote Monitoring by CCTV - MEICA | Other | Maintenance
Remote Monitoring of South East Sites by CCTV | Other | Maintenance
Capital Maintenance Ops Delivery South West | Other | Maintenance |  |  | <250k | <250k | <250k | <250k | <250k | <250k | <250k | <500k | <2500k |  |  | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance
Capital Maintenance Ops Delivery South East | Other | Maintenance |  |  | <250k | <250k | <250k | <250k | <250k | <250k | <250k | <500k | <2500k |  |  | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance
Capital Maintenance Ops Delivery North | Other | Maintenance |  |  | <500k | <500k | <500k | <500k | <500k | <500k | <500k | <1000k | <2500k |  |  | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance
LIDAR Data Capture Winter 2016 | Other | Modelling
LIDAR Data Capture Winter 2017 | Other | Modelling
Northern Area - Topographic Survey Requirements | Other | Modelling
South East Topographic Data Collection | Other | Modelling
EA Recharge Costs | Other | Other
NRW Civil Engineering Framework Agreement | Other | Other
Reservoir High Risk Designation | Other | Other
IPP 15-16 | Other | Property Level Protection
IPP Replacement Fund | Other | Property Level Protection
Wales FCRM Fleet Asset Replacement Programme 15/16 | Other | Vehicles
Cilrhedyn Bridge | Pembrokeshire - Sir Benfro | Maintenance | <50k | <5k | [8 empty] | <50k | Maintenance | Maintenance
Prendergast Mill Bank Repair | Pembrokeshire - Sir Benfro | Maintenance | <50k | <5k | [8 empty] | <50k | Maintenance | Maintenance
Pont y Cerbyd Access Improvements | Pembrokeshire - Sir Benfro | Maintenance | <5k | [9 empty] | <5k | Maintenance
Pont y Cerbyd Reservoir Section 10 | Pembrokeshire - Sir Benfro | Maintenance | <50k | [9 empty] | <50k | Maintenance
Tenby Buoy Assessment | Pembrokeshire - Sir Benfro | Maintenance | <50k | [9 empty] | <50k | Maintenance
Dyffryn Gwaun Wetland Creation | Pembrokeshire - Sir Benfro | Biodiversity and Habitat Enhancement | <5k | [9 empty] | <5k | Construction | [12 empty] | 1
Little Haven | Pembrokeshire - Sir Benfro | Maintenance |  | <50k | [8 empty] | <50k |  | Maintenance
Stepaside Defences | Pembrokeshire - Sir Benfro | Maintenance |  | <50k | [8 empty] | <50k |  | Maintenance
Solva & Middle Mill NFM Assessment | Pembrokeshire - Sir Benfro | Other |  | <50k | <50k | <50k | [6 empty] | <100k |  | Study | Study | Study
Cartlett Brook Flood Wall | Pembrokeshire - Sir Benfro | Maintenance
Haverfordwest | Pembrokeshire - Sir Benfro | Defence | [5 empty] | <50k | <250k | <250k |  |  | <500k | [5 empty] | Appraisal | Design | Design
Abermad PLP | Pembrokeshire - Sir Benfro | Property Level Protection
Cilmery Gauging Station Refurbishment | Powys - Powys | Maintenance | <50k | <5k | [8 empty] | <50k | Maintenance | Maintenance
Brecon Weir Repairs | Powys - Powys | Maintenance | <50k | <50k | [8 empty] | <100k | Maintenance | Maintenance
Llanidloes Deshoal | Powys - Powys | Maintenance | <50k | <50k | [8 empty] | <100k | Maintenance | Maintenance
Pan Teg Weir | Powys - Powys | Maintenance | <50k | [9 empty] | <50k | Maintenance
Esgair Carnau - Bank Protection | Powys - Powys | Maintenance | <50k | [9 empty] | <50k | Maintenance
Ystradgynlais Flood Risk Management | Powys - Powys | Defence | <50k | [9 empty] | <50k | Completion
Brecon - Structural Assessment | Powys - Powys | Maintenance |  | <50k | [8 empty] | <50k |  | Study
Waen Rydd SSSI - Hydrological Assessment | Powys - Powys | Biodiversity and Habitat Enhancement
Brecon Dinas Lodge Scour Repairs | Powys - Powys | Maintenance
Glasbury Wall - Left Bank Repairs | Powys - Powys | Maintenance
Haimwood Outfall and Culvert | Powys - Powys | Maintenance
Llys Tawel Wall, Ystradgynlais | Powys - Powys | Maintenance |  |  |  | <50k | [6 empty] | <50k |  |  |  | Maintenance
Llanidloes Initial Assessment | Powys - Powys | Defence |  |  | <50k | [7 empty] | <50k |  |  | Study
Trehelig Door and Argae Refurbishment | Powys - Powys | Maintenance |  |  | <50k | [7 empty] | <50k |  |  | Maintenance
Llanwrytyd Wells | Powys - Powys | Maintenance |  |  | <50k | [7 empty] | <50k |  |  | Maintenance
Glasbury - Structural Assessment | Powys - Powys | Maintenance |  |  | <50k | [7 empty] | <50k |  |  | Study
Brecon Embankment Repairs and Deshoal | Powys - Powys | Maintenance |  |  | <50k | [7 empty] | <50k |  |  | Maintenance
Llanidloes Deshoal | Powys - Powys | Maintenance |  |  |  |  | <50k | [5 empty] | <50k |  |  |  |  | Maintenance
Builth Wells PLP (Right Bank) | Powys - Powys | Property Level Protection
Rhondda Walls- Structural Assessment | Rhondda Cynon Taf - Rhondda Cynon Taf | Maintenance | <50k | [9 empty] | <50k | Study
Hawthorn Deshoal | Rhondda Cynon Taf - Rhondda Cynon Taf | Maintenance | <50k | <50k | [8 empty] | <100k | Maintenance | Maintenance
Mountain Ash Embankment | Rhondda Cynon Taf - Rhondda Cynon Taf | Maintenance | <50k | [9 empty] | <50k | Maintenance
Mynydd Ton Peatbog Restoration | Rhondda Cynon Taf - Rhondda Cynon Taf | Biodiversity and Habitat Enhancement | <50k | [9 empty] | <50k | Construction | [12 empty] | 12
River Rhondda Asset Management Plan | Rhondda Cynon Taf - Rhondda Cynon Taf | Maintenance |  | <500k | <500k | <2500k | <2500K |  | <2500k | <1000k |  | >5000k | >5000k |  | Appraisal | Design | Construction | Construction |  | Construction | Construction |  | Construction
Nant Aman Culvert Screen | Rhondda Cynon Taf - Rhondda Cynon Taf | Maintenance |  | <50k | [8 empty] | <50k |  | Maintenance
Mountain Ash - Phase 2 | Rhondda Cynon Taf - Rhondda Cynon Taf | Maintenance |  | <50k | <100k | [7 empty] | <100k |  | Maintenance | Maintenance
Treforest Ind Est - Structural Assessment | Rhondda Cynon Taf - Rhondda Cynon Taf | Maintenance |  | <50k |  |  |  |  | <1000k | <2500k | <2500k |  | <5000k |  | Study |  |  |  |  | Construction | Construction | Construction
Assessment of NFM Impacts in the Rhondda Valley | Rhondda Cynon Taf - Rhondda Cynon Taf | Other |  | <50k | [8 empty] | <50k |  | Study
Sion Street Pontypridd - Wall Refurbishment | Rhondda Cynon Taf - Rhondda Cynon Taf | Maintenance
Treforest Embankment Reprofile and Repairs | Rhondda Cynon Taf - Rhondda Cynon Taf | Maintenance
Pontyclun Initial Assessment | Rhondda Cynon Taf - Rhondda Cynon Taf | Defence |  |  | <50k | [7 empty] | <50k |  |  | Appraisal
Glyntaff Initial Assessment | Rhondda Cynon Taf - Rhondda Cynon Taf | Defence |  |  | <50k | [7 empty] | <50k |  |  | Appraisal
Hirwaun - New FAS | Rhondda Cynon Taf - Rhondda Cynon Taf | Defence |  |  | <250k | [7 empty] | <250k |  |  | Appraisal
Robertstown - New FAS | Rhondda Cynon Taf - Rhondda Cynon Taf | Defence | [6 empty] | <100k | <250k | <2500k |  | <2500k | [6 empty] | Appraisal | Design | Construction
Aberdare Culvert Inspections | Rhondda Cynon Taf - Rhondda Cynon Taf | Maintenance |  |  |  | <50k | [6 empty] | <50k |  |  |  | Maintenance
Porth/Hopkinstown Wall Repairs | Rhondda Cynon Taf - Rhondda Cynon Taf | Maintenance |  |  |  | <50k | [6 empty] | <50k |  |  |  | Maintenance
Pontyclun Deshoal | Rhondda Cynon Taf - Rhondda Cynon Taf | Maintenance |  |  |  | <50k | [6 empty] | <50k |  |  |  | Maintenance
Rhondda Confluence | Rhondda Cynon Taf - Rhondda Cynon Taf | Maintenance |  |  | <50k | [7 empty] | <50k |  |  | Maintenance
Treforest Deshoal | Rhondda Cynon Taf - Rhondda Cynon Taf | Maintenance |  |  |  | <50k | [6 empty] | <50k |  |  |  | Maintenance
Ynysddu - Structural Assessment | Rhondda Cynon Taf - Rhondda Cynon Taf | Maintenance |  |  | <50k | [7 empty] | <50k |  |  | Maintenance
Trehafod Blockstone Repairs | Rhondda Cynon Taf - Rhondda Cynon Taf | Maintenance |  |  |  | <50k | [6 empty] | <50k |  |  |  | Maintenance
Loughor Flood Bank Repairs | Swansea - Abertawe | Maintenance | <5k | [9 empty] | <5k | Maintenance
Ynystanglws Bank Wall Improvements | Swansea - Abertawe | Maintenance | <50k | [9 empty] | <50k | Maintenance
Ynystawe Park Floodbank Repair | Swansea - Abertawe | Maintenance | <50k | [9 empty] | <50k | Maintenance
Crofty Surveying | Swansea - Abertawe | Modelling | <5k | [9 empty] | <5k | Maintenance
Pontarddulais Flood Risk Management | Swansea - Abertawe | Defence | <1000k | <50k | [8 empty] | <1000k | Construction | Construction | [8 empty] | 224 | 22
Cwm Ivy Marsh Managed Realignment | Swansea - Abertawe | Biodiversity and Habitat Enhancement | <50k | <50k | <50k | <50k | [6 empty] | <100k | Completion | Completion | Completion | Completion | [10 empty] | 38
Penclawdd Flood Risk Management | Swansea - Abertawe | Defence | <5k | [9 empty] | <5k | Completion
Pontardawe Industrial Area Defence | Swansea - Abertawe | Defence |  | <250k | [8 empty] | <250k |  | Design
Llansamlet Initial Assessment | Swansea - Abertawe | Defence |  | <50k | <50k | <250k | [6 empty] | <250k |  | Study | Appraisal | Design
Cwm Ivy Land Purchase | Swansea - Abertawe | Biodiversity and Habitat Enhancement
Lower Swansea Vale Flood Risk Management | Swansea - Abertawe | Defence | [21 empty] | 6 | 284
Gorseinon Gravel Removal | Swansea - Abertawe | Maintenance
Gowerton Headwall and Floodbank Repair | Swansea - Abertawe | Maintenance
Llanmorlais Tidal Bank Repairs | Swansea - Abertawe | Maintenance
Pontarddulais Gravel Management 16/17 | Swansea - Abertawe | Maintenance
Gorseinon FAS | Swansea - Abertawe | Defence |  |  | <50k | [7 empty] | <50k |  |  | Study
Contribution to Coldbrook FAS | The Vale of Glamorgan - Bro Morgannwg | Defence | <1000k | [9 empty] | <1000k | Other
Cadoxton Sea Door Improvements | The Vale of Glamorgan - Bro Morgannwg | Maintenance | <250k | [9 empty] | <250k | Maintenance
River Cadaxton Improvements | The Vale of Glamorgan - Bro Morgannwg | Maintenance | <250k | <250k | <1000K | <2500k | [6 empty] | <2500k | Design | Design | Maintenance | Maintenance | [6 empty] | TBC | TBC
Cowbridge FAS - Replacement Sleepers and Toe Drain | The Vale of Glamorgan - Bro Morgannwg | Maintenance
Afon Llwyd Integrated Catchment Model | Torfaen - Tor-faen | Modelling | <50k | [9 empty] | <50k | Other
Llanyrafon, Cwmbran - Improve FAS | Torfaen - Tor-faen | Maintenance |  | <100k | [8 empty] | <100k |  | Maintenance
Ponthir - Structural Assessment | Torfaen - Tor-faen | Maintenance |  | <50k | [8 empty] | <50k |  | Study
Graig Lane Pumping Station Efficiency Improvements | Wrexham - Wrecsam | Other |  | <50k | <50k | <50k | <100k | [5 empty] | <100k |  | Study | Study | Study | Study
Trevalyn Pumping Station Review | Wrexham - Wrecsam | Other |  | <50k | <50k | <50k | <50k | <250k |  |  |  |  | <250k |  | Study | Study | Study | Study | Study
Graig Lane Embankment Refurbishment | Wrexham - Wrecsam | Maintenance
Manley Hall Gauging Station Refurbishment | Wrexham - Wrecsam | Maintenance
Rossett Flood Wall Investigation | Wrexham - Wrecsam | Maintenance
Bangor on Dee Embankment Slippage | Wrexham - Wrecsam | Maintenance |  |  |  | <100k | <100k | <2500k |  |  |  |  | <2500k |  |  |  | Design | Construction | Construction