## Sheet1
FUNDED AND INDICATIVE MEDIUM TERM PLAN FOR FLOOD RISK MANAGEMENT WALES CAPITAL PROGRAMME (2015/2016 ONWARDS)
Approved May 2016
Project | Local Authority | Project Type | Confirmed Funding | Indicative funding | [8 empty] | TOTAL CONFIRMED AND INDICATIVE FUNDING (£) | Project Stage/ Activity | [9 empty] | NUMBER OF HOUSEHOLDS WITH REDUCED FLOOD RISK | NUMBER OF BUSINESSES WITH REDUCED FLOOD RISK | NUMBER OF PROPERTIES ISSUED WITH INDIVIDUAL PROTECTION MEASURES | UK BIODIVERSITY ACTIONPLAN HABITAT CREATED (TERRESTRIAL) (Ha) | UK BIODIVERSITY ACTIONPLAN HABITAT CREATED (INTER-TIDAL) (Ha)
|  |  | 2016/17 Yr 1 (£) | 2017/18 Yr 2 (£) | 2018/19 Yr 3 (£) | 2019/20 Yr 4 (£) | 2020/21 Yr 5 (£) | 2021/22 Yr 6 (£) | 2022/23 Yr 7 (£) | 2023/24 Yr 8 (£) | 2024/25 Yr 9 (£) | 2025 Onwards Yr 10+ (£) | 2016-17 TO 2025+ | 2016/17 Yr 1 (£) | 2017/18 Yr 2 (£) | 2018/19 Yr 3 (£) | 2019/20 Yr 4 (£) | 2020/21 Yr 5 (£) | 2021/22 Yr 6 (£) | 2022/23 Yr 7 (£) | 2023/24 Yr 8 (£) | 2024/25 Yr 9 (£) | 2025 Onwards Yr 10+ (£) | 2015-16 TO 2024+ TOTAL | 2015-16 TO 2024+ TOTAL | 2015-16 TO 2024+ TOTAL | 2015-16 TO 2024+ TOTAL | 2015-16 TO 2024+ TOTAL
Aberbeeg Flow Monitoring Station | Blaenau Gwent - Blaenau Gwent | Maintenance | <5k | [9 empty] | <5k | Completion
Ebbw FAS - Initial Assessment | Blaenau Gwent - Blaenau Gwent | Defence |  | <50k | [8 empty] | <50k |  | Appraisal
Abertillery/Six Bells | Blaenau Gwent - Blaenau Gwent | Maintenance |  |  |  | <50k | [6 empty] | <50k |  |  |  | Maintenance
Abertillery & Six Bells - Structural Assessment | Blaenau Gwent - Blaenau Gwent | Maintenance |  |  |  |  | <50k | <50k |  |  |  |  | <100k |  |  |  |  | Appraisal | Maintenance
Aberbeeg Woodland Wall Replacement | Blaenau Gwent - Blaenau Gwent | Maintenance | <500k | [9 empty] | <500k | Maintenance
Afon Fach Pyle Berm | Bridgend - Pen-yr-Bont ar Ogwr | Maintenance | <5k | [9 empty] | <5k | Maintenance
River Ogmore Access Ladders | Bridgend - Pen-yr-Bont ar Ogwr | Maintenance | <5k | [9 empty] | <5k | Maintenance
Ogmore Vale FRM Hydraulic Modelling - Phase 2 | Bridgend - Pen-yr-Bont ar Ogwr | Modelling | <5k | [9 empty] | <5k
Keepers Lodge Ramp | Bridgend - Pen-yr-Bont ar Ogwr | Maintenance | <50k | [9 empty] | <50k | Completion
Pencoed | Bridgend - Pen-yr-Bont ar Ogwr | Maintenance | <50k | [9 empty] | <50k | Maintenance
Waterton & Treoes | Bridgend - Pen-yr-Bont ar Ogwr | Maintenance |  | <50k | [8 empty] | <50k |  | Maintenance
Tondu Road Access Track | Bridgend - Pen-yr-Bont ar Ogwr | Maintenance | <50k | [9 empty] | <50k | Maintenance
Nant Brynglas Trash Screen | Bridgend - Pen-yr-Bont ar Ogwr | Maintenance | <50k | [9 empty] | <50k | Maintenance
Pandy Farm Revetment Repair | Bridgend - Pen-yr-Bont ar Ogwr | Maintenance |  | <50k | [8 empty] | <50k |  | Maintenance
Coytrahen Station Refurbishment | Bridgend - Pen-yr-Bont ar Ogwr | Maintenance | <100k | <5k | [8 empty] | <100k | Construction | Completion
Bridgend Maintenance | Bridgend - Pen-yr-Bont ar Ogwr | Maintenance | <50k | <100k | [8 empty] | <250k | Maintenance | Maintenance
Maesteg | Bridgend - Pen-yr-Bont ar Ogwr | Maintenance |  |  |  | <50k | <50k | <250k |  |  |  |  | <250k |  |  |  | Appraisal | Design | Construction |  |  |  |  | TBC | TBC
Aberkenfig FAS | Bridgend - Pen-yr-Bont ar Ogwr | Defence |  | <5k | <50k | <50k | <250k | [5 empty] | <500k |  | Appraisal | Design | Construction | Construction | [5 empty] | TBC | TBC
Corbett's Lane, Caerphilly - IPP | Caerphilly - Caerffili | Property Level Protection |  | <50k | [8 empty] | <50k |  | Other | [10 empty] | TBC
Tan y Bryn - Floodbank Improvements | Caerphilly - Caerffili | Maintenance |  |  | <50k | [7 empty] | <50k |  |  | Maintenance
British Legion, Machen - Gap in defences | Caerphilly - Caerffili | Maintenance |  | <50k | [8 empty] | <50k |  | Maintenance
Coedypia, Ystrad Mynach - Structural Assessment | Caerphilly - Caerffili | Maintenance |  |  |  | <50k | [6 empty] | <50k |  |  |  | Appraisal
Bedwas Walls - Structural Assessment | Caerphilly - Caerffili | Maintenance |  |  |  |  | <50k | [5 empty] | <50k |  |  |  |  | Appraisal
Ystrad Mynach Deshoal and Embankment Repairs | Caerphilly - Caerffili | Maintenance | <50k | [9 empty] | <50k | Maintenance
Llanbradach - New Embankment | Caerphilly - Caerffili | Defence |  |  | <50k | [7 empty] | <50k |  |  | Appraisal | [7 empty] | TBC | TBC
Green Row & Glan Yr Afon, Machen - IPP | Caerphilly - Caerffili | Property Level Protection | [5 empty] | <100k |  |  |  |  | <100k | [5 empty] | Other | [6 empty] | TBC
Bridge St, Newbridge - New FAS | Caerphilly - Caerffili | Defence |  |  |  |  | <50k | <50k |  |  |  |  | <100k |  |  |  |  | Appraisal | Design |  |  |  |  | TBC | TBC
Dyffryn Meadows Ind Est - Improve FAS | Caerphilly - Caerffili | Maintenance |  |  |  |  | <50k | <500k |  |  |  |  | <1,000k |  |  |  |  | Design | Construction
Tyn y waun, Machen - New FAS | Caerphilly - Caerffili | Defence |  |  |  |  | <500k | <500k |  |  |  |  | <1,000k |  |  |  |  | Construction | Construction |  |  |  |  | TBC | TBC
Risca Flood Risk Management | Caerphilly - Caerffili | Defence | <1,000k | <50k | [8 empty] | <1,000k | Construction | Completion | [8 empty] | 259 | 19
St Fagan's, Cardiff - IPP | Cardiff - Caerdydd | Property Level Protection |  | <50k | [8 empty] | <50k |  | Other | [10 empty] | TBC
Cardiff Remedial Wall Repairs (Ops Delivery) | Cardiff - Caerdydd | Maintenance |  |  | <50k | [7 empty] | <50k |  |  | Maintenance
Cardiff Embankment Repairs (Ops Delivery) | Cardiff - Caerdydd | Maintenance |  |  |  | <50k | [6 empty] | <50k |  |  |  | Maintenance
Cardiff Wall Repairs (Ops Delivery) | Cardiff - Caerdydd | Maintenance |  |  |  |  | <50k | [5 empty] | <50k |  |  |  |  | Maintenance
Mellingriffith - Bank Repairs | Cardiff - Caerdydd | Maintenance |  |  | <50k | [7 empty] | <50k |  |  | Maintenance
Ball Road, Llanrumney | Cardiff - Caerdydd | Maintenance |  |  |  | <50k | [6 empty] | <50k |  |  |  | Maintenance
Began Farm | Cardiff - Caerdydd | Maintenance |  |  |  |  | <50k | [5 empty] | <50k |  |  |  |  | Maintenance
Cardiff Bay Siltation Monitoring | Cardiff - Caerdydd | Maintenance | <50k | [9 empty] | <50k | Other
Cardiff FAS - Structural Assessment | Cardiff - Caerdydd | Maintenance |  |  |  | <50k | [6 empty] | <50k |  |  |  | Maintenance
Broadway Reen Tipping Weir | Cardiff - Caerdydd | Maintenance | <50k | [9 empty] | <50k | Other
Cardiff Sea Defences | Cardiff - Caerdydd | Defence |  | <50k | <50k | [7 empty] | <100k |  | Appraisal | Design | [7 empty] | TBC | TBC
Cardiff FAS - Scheme Review | Cardiff - Caerdydd | Defence |  |  | <100k | [7 empty] | <100k |  |  | Study
Leckwith Bridge Industrial Estate | Cardiff - Caerdydd | Maintenance | <250k | [9 empty] | <250k | Construction
Llanrumney - Retreat of Defences | Cardiff - Caerdydd | Maintenance |  |  |  |  | <250k | [5 empty] | <250k |  |  |  |  | Construction
Roath and Rhymney Flood Risk Management | Cardiff - Caerdydd | Defence | <2,500k | >5,000k | <1,000k | <100k | [6 empty] | >5,000k | Construction | Construction | Construction | Completion | [6 empty] | 360 | 51
Llanwrda Wall | Carmarthenshire - Sir Gaerfyrddin | Maintenance | <5k | [9 empty] | <5k | Maintenance
Tywi Access Improvements | Carmarthenshire - Sir Gaerfyrddin | Maintenance | <50k | [9 empty] | <50k | Maintenance
Pendine Sluice and Gate Refurbishment | Carmarthenshire - Sir Gaerfyrddin | Maintenance | <50k | [9 empty] | <50k | Maintenance
Pendine Access Track | Carmarthenshire - Sir Gaerfyrddin | Maintenance | <50k | [9 empty] | <50k | Maintenance
Pontyates Floodbank | Carmarthenshire - Sir Gaerfyrddin | Maintenance | <50k | [9 empty] | <50k | Maintenance
Whitland Coping Stone Replacement | Carmarthenshire - Sir Gaerfyrddin | Maintenance | <50k | [9 empty] | <50k | Maintenance
Pwll Flood Risk Management | Carmarthenshire - Sir Gaerfyrddin | Maintenance | <50k | [9 empty] | <50k | Maintenance | [9 empty] | 153 | 5
Blockstone Repair Ammanford | Carmarthenshire - Sir Gaerfyrddin | Maintenance |  | <50k | [8 empty] | <50k |  | Maintenance
Carmarthen | Carmarthenshire - Sir Gaerfyrddin | Maintenance |  | <50k | <5k | [7 empty] | <50k |  | Maintenance | Maintenance
Dafen Vegitation Clearance | Carmarthenshire - Sir Gaerfyrddin | Maintenance | <50k | [9 empty] | <50k | Maintenance
Hendy Flood Risk Mapping Study | Carmarthenshire - Sir Gaerfyrddin | Modelling | <50k | [9 empty] | <50k | Study
Lliedi Blockstone Repairs | Carmarthenshire - Sir Gaerfyrddin | Maintenance | <50k | [9 empty] | <50k | Maintenance
Clog y Fran Bank Improvements | Carmarthenshire - Sir Gaerfyrddin | Maintenance | <50k | [9 empty] | <50k | Maintenance
Trothy Catchment Habitat Creation Project | Carmarthenshire - Sir Gaerfyrddin | Biodiversity and Habitat Enhancement | <50k | [9 empty] | <50k | Other | [12 empty] | 10
Carmarthen Topographic Survey - Phase 1 | Carmarthenshire - Sir Gaerfyrddin | Modelling | <50k | [9 empty] | <50k | Study
Abergwili Access Improvements | Carmarthenshire - Sir Gaerfyrddin | Maintenance | <50k | [9 empty] | <50k | Maintenance
Whitland Defences Underpinning | Carmarthenshire - Sir Gaerfyrddin | Maintenance | <50k | [9 empty] | <50k | Maintenance
Pwll FAS - Underpin Wall | Carmarthenshire - Sir Gaerfyrddin | Maintenance | <50k | [9 empty] | <50k | Maintenance
Laugharne Mill Leat De Silt | Carmarthenshire - Sir Gaerfyrddin | Maintenance |  | <50k | <50k | [7 empty] | <100k |  | Maintenance | Maintenance
Llanybydder FAS | Carmarthenshire - Sir Gaerfyrddin | Defence |  |  | <50k | <50k | <100k | [5 empty] | <250k |  |  | Appraisal | Design | Construction | [5 empty] | TBC | TBC
North Dafen Attenuation Pond | Carmarthenshire - Sir Gaerfyrddin | Defence | <250k | <100k | [8 empty] | <250k | Maintenance | Maintenance | [8 empty] | TBC | TBC
Machynys Flood Defence Maintenance | Carmarthenshire - Sir Gaerfyrddin | Maintenance | <1,000k | [9 empty] | <1,000k | Maintenance
Llanrhystud Ford | Ceredigion - Sir Ceredigion | Maintenance | <50k | [9 empty] | <50k | Maintenance
Pentre Cwrt and Llandysul - Phase 1 | Ceredigion - Sir Ceredigion | Modelling | <50k | [9 empty] | <50k | Study
Aberystwyth Initial Assessment | Ceredigion - Sir Ceredigion | Defence | <50k | [9 empty] | <50k | Appraisal | [9 empty] | TBC | TBC
Lampeter and Llanybydder - Phase 1 | Ceredigion - Sir Ceredigion | Modelling | <50k | [9 empty] | <50k | Study
Aberaeron | Ceredigion - Sir Ceredigion | Maintenance |  |  |  | <50k | [6 empty] | <50k |  |  |  | Maintenance
Lampeter Initial Assessment | Ceredigion - Sir Ceredigion | Defence | <50k | [9 empty] | <50k | Appraisal | [9 empty] | TBC | TBC
Glan yr Afon Flood Defence Improvements | Ceredigion - Sir Ceredigion | Maintenance | <50k | [9 empty] | <50k | Maintenance
Mwldan Overflow Outfall Improvements | Ceredigion - Sir Ceredigion | Maintenance |  | <50k | [8 empty] | <50k |  | Maintenance
Cwmystwyth Station & Weir Refurbishment | Ceredigion - Sir Ceredigion | Maintenance | <50k | <50k | <100k | [7 empty] | <250k | Design | Construction | Construction
Llechryd Tree Catcher | Ceredigion - Sir Ceredigion | Defence | <250k | [9 empty] | <250k | Construction
Parc yr Onnen | Ceredigion - Sir Ceredigion | Defence | <250k | [9 empty] | <250k | Construction
Morfa Madryn Compensation Habitat Creation | Conwy - Conwy | Biodiversity and Habitat Enhancement | <5k | [9 empty] | <5k | Other
Llanfair TH-Nant Barrog Phase 2 | Conwy - Conwy | Defence | <50k | [9 empty] | <50k | Construction
Mochdre Initial Assessment | Conwy - Conwy | Maintenance |  | <50k | [8 empty] | <50k |  | Appraisal | [8 empty] | TBC | TBC
Maenan Stream Flood Wall Improvements | Conwy - Conwy | Maintenance | <50k | [9 empty] | <50k | Maintenance
Ffynnon y Ddol Culvert replacement / widening | Conwy - Conwy | Maintenance |  | <50k | [8 empty] | <50k |  | Maintenance
Gele Bi-pass culvert - Screen removal & channel re-grade | Conwy - Conwy | Maintenance |  | <50k | [8 empty] | <50k |  | Maintenance
Abergele Tidal Flood Risk Study | Conwy - Conwy | Modelling |  | <50k | [8 empty] | <50k |  | Study
Conwy Valley Phase 3 | Conwy - Conwy | Modelling | <50k | [9 empty] | <50k | Study
Spinnies outfall re-design & replacement | Conwy - Conwy | Maintenance |  | <50k | [8 empty] | <50k |  | Maintenance
Llanfairfechan Weir refurbishment x 4 | Conwy - Conwy | Maintenance |  | <50k | <50k | <50k | <50k | [5 empty] | <50k |  | Maintenance | Maintenance | Maintenance | Maintenance
Afon Wydden Spillway Works | Conwy - Conwy | Maintenance | <250k | [9 empty] | <250k | Maintenance
Dyffryn Conwy Flood Risk Management | Conwy - Conwy | Defence | <250k | [9 empty] | <250k | Construction | [9 empty] | 28 | 49
Llanfair Talhaiarn Phase 3 | Conwy - Conwy | Defence | <250k | <1,000k | <100k | [7 empty] | <1,000k | Construction | Construction | Completion | [7 empty] | TBC | TBC
Marine Lake Embankment | Denbighshire - Sir Ddinbych | Maintenance | <50k | [9 empty] | <50k | Maintenance
St Asaph Phase 3 Works City Bridge to Elwy Weir | Denbighshire - Sir Ddinbych | Maintenance | <50k | [9 empty] | <50k | Maintenance
Corwen Roof Repairs | Denbighshire - Sir Ddinbych | Maintenance | <50k | [9 empty] | <50k | Maintenance
Rhyl Cut Access Improvements | Denbighshire - Sir Ddinbych | Maintenance | <50k | [9 empty] | <50k | Maintenance
River Elwy Erosion Repairs | Denbighshire - Sir Ddinbych | Maintenance | <50k | [9 empty] | <50k | Maintenance
Rhyl and Prestatyn Fluvial Modelling Study | Denbighshire - Sir Ddinbych | Modelling | <50k | [9 empty] | <50k | Study
Tidal outfall at Rhyl PS outfall / tidal flap replacement | Denbighshire - Sir Ddinbych | Maintenance |  | <50k | [8 empty] | <50k |  | Maintenance
Retreat Flood Embankment - Elwy | Denbighshire - Sir Ddinbych | Maintenance |  | <5k | <50k | [7 empty] | <50k |  | Maintenance | Maintenance
Maes Maelor Bog Creation | Denbighshire - Sir Ddinbych | Biodiversity and Habitat Enhancement | <50k | [9 empty] | <50k | Other | [12 empty] | 9
Rhyl and Prestatyn Tidal Flood Risk Study | Denbighshire - Sir Ddinbych | Modelling | <50k | [9 empty] | <50k | Study
Modelling Tidal Flood Risk - Towyn, Kinmel | Denbighshire - Sir Ddinbych | Modelling |  | <50k | [8 empty] | <50k |  | Study
Warren Drive Trash screen | Denbighshire - Sir Ddinbych | Maintenance | <50k | [9 empty] | <50k | Maintenance
Dyserth | Denbighshire - Sir Ddinbych | Maintenance |  | <50k | <50k |  | <2,500k | [5 empty] | <2,500k |  | Appraisal | Design |  | Construction
NE Wales Trash Screen Designs | Denbighshire - Sir Ddinbych | Maintenance | <1,000k | <1,000k | <2,500k | [7 empty] | <5,000k | Design | Design | Construction
St Asaph FCRM | Denbighshire - Sir Ddinbych | Defence | <2,500k | <5,000k | <500k | [7 empty] | >5,000k | Construction | Construction | Completion | [7 empty] | 510 | 38
Work arising from the Clwyd strategy | Denbighshire - Sir Ddinbych | Defence | [6 empty] | >5,000k | >5,000k | >5,000k | >5,000k | >5,000k | [6 empty] | Construction | Construction | Construction | Construction | TBC | TBC
Bank stablisation Thornleigh U/S of pumping station | Flintshire - Sir y Fflint | Maintenance |  | <50k | [8 empty] | <50k |  | Maintenance
Bretton Drain Initial Assessment | Flintshire - Sir y Fflint | Defence |  | <50k | [8 empty] | <50k |  | Appraisal
Rowleys Pumping Station Weedscreen | Flintshire - Sir y Fflint | Maintenance | <50k | [9 empty] | <50k | Maintenance
Hawarden embankment - erosion Rowleys outfall | Flintshire - Sir y Fflint | Maintenance |  | <50k | [8 empty] | <50k |  | Maintenance
Broughton Brook and Queensferry Drain Flood Mapping Study | Flintshire - Sir y Fflint | Modelling | <5k | <50k | [8 empty] | <50k | Study | Study
Wepre Gutter Pilling Works | Flintshire - Sir y Fflint | Maintenance | <50k | [9 empty] | <50k | Maintenance
Pontblyddyn project | Flintshire - Sir y Fflint | Defence | <50k |  | <1,000k | [7 empty] | <1,000k | Design |  | Construction | [7 empty] | 15
Work arising from the Dee strategy | Flintshire - Sir y Fflint | Defence |  |  | >5,000k |  |  | >5,000k |  |  |  | >5,000k | >5,000k |  |  | Construction |  |  | Construction |  |  |  | Construction | TBC | TBC
Llyn Tegid Sluice - Fish Migration Investigation | Gwynedd - Gwynedd | Maintenance | <5k | [9 empty] | <5k | Maintenance
Mawddach Modelling | Gwynedd - Gwynedd | Modelling | <5k | [9 empty] | <5k | Study
Llanddulas and Bontnewydd Flood Analysis and Modelling | Gwynedd - Gwynedd | Modelling | <5k | [9 empty] | <5k | Study
Porthmadog Flood Risk Management | Gwynedd - Gwynedd | Defence | <5k | [9 empty] | <5k | Appraisal
Harlech Initial Assessment | Gwynedd - Gwynedd | Defence |  | <50k | [8 empty] | <50k |  | Appraisal
Aberdesach Flood Improvement Works | Gwynedd - Gwynedd | Maintenance | <50k | [9 empty] | <50k | Maintenance
Ty Uchaf - Cors y Sarnau Wetland Project | Gwynedd - Gwynedd | Biodiversity and Habitat Enhancement | <50k | [9 empty] | <50k | Other | [12 empty] | 19
Cynefail Gauging Station | Gwynedd - Gwynedd | Maintenance | <50k | [9 empty] | <50k | Maintenance
Penllyn Tywyn Outfall | Gwynedd - Gwynedd | Maintenance |  | <50k | [8 empty] | <50k |  | Maintenance
Draenogau Tidal Doors | Gwynedd - Gwynedd | Maintenance | <50k | [9 empty] | <50k | Maintenance
Harlech Weedscreens | Gwynedd - Gwynedd | Maintenance | <50k | [9 empty] | <50k | Maintenance
Tywyn and Bryncrug Bathymetric Surveys | Gwynedd - Gwynedd | Modelling |  | <50k | [8 empty] | <50k |  | Study
Llyn Tegid Gravel Removal | Gwynedd - Gwynedd | Maintenance | <50k | [9 empty] | <50k | Maintenance
Llandanwg Breakwater | Gwynedd - Gwynedd | Maintenance |  | <50k | [8 empty] | <50k |  | Maintenance
Tidal Dyfi Strategy | Gwynedd - Gwynedd | Defence |  | <50k | <50k | [7 empty] | <50k |  | Appraisal | Design
CWRT Chamber & Weedscreen | Gwynedd - Gwynedd | Maintenance |  | <50k | <50k | [7 empty] | <50k |  | Maintenance | Maintenance
Ty Gwyn Tidal doors and penstock renewal | Gwynedd - Gwynedd | Maintenance | <50k | [9 empty] | <50k | Maintenance
Fairbourne Flood Risk Management Scheme | Gwynedd - Gwynedd | Defence | <50k | [9 empty] | <50k | Completion | [9 empty] | 410 | 10
Beddgelert | Gwynedd - Gwynedd | Maintenance |  | <50k | [8 empty] | <50k |  | Maintenance
Talsarnau Sea Defence | Gwynedd - Gwynedd | Maintenance |  |  | <50k | [7 empty] | <50k |  |  | Maintenance
Dysynni Low Level Outfall Tidal Doors Replacement | Gwynedd - Gwynedd | Maintenance | <250k | [9 empty] | <250k | Maintenance
Nant Iago, Llanbedrog | Gwynedd - Gwynedd | Maintenance |  | <50k | <100k | [7 empty] | <250k |  | Design | Maintenance
Garndolbenmaen GS Viability | Gwynedd - Gwynedd | Maintenance | <5k | <50k | <250k | [7 empty] | <250k | Appraisal | Design | Maintenance
Erch penstocks | Gwynedd - Gwynedd | Maintenance |  | <50k | <250k | [7 empty] | <250k |  | Design | Maintenance
Dolgellau (Wnion and Arran) Flood Risk Management | Gwynedd - Gwynedd | Defence | <250k | <50k | <50k | <5k | <5k | [5 empty] | <250k | Construction | Construction | Construction | Completion | Completion | [5 empty] | 182 | 128
Llyn Tegid Section 10 Repairs | Gwynedd - Gwynedd | Maintenance | <50k | <250k | [8 empty] | <250k | Design | Maintenance
Ffriog Cliffs Sea Defence Repairs | Gwynedd - Gwynedd | Maintenance | <250k | [9 empty] | <250k | Maintenance
Mochras Floodbank and Tidal doors | Gwynedd - Gwynedd | Maintenance |  |  |  | <250k | <250k | [5 empty] | <500k |  |  |  | Maintenance | Maintenance
Porthmadog Tidal Structures | Gwynedd - Gwynedd | Defence | <100k | <100k | <500k | [7 empty] | <1,000k | Design | Construction | Construction | [7 empty] | TBC | TBC
Vale of Ffestiniog Land Purchase | Gwynedd - Gwynedd | Biodiversity and Habitat Enhancement | <1,000k | [9 empty] | <1,000k | Other
Vale of Ffestiniog Compensation Habitat Creation | Gwynedd - Gwynedd | Biodiversity and Habitat Enhancement | <250k | <250k | <1,000k | <100k | [6 empty] | <2,500k | Other | Other | Other | Other
Porthmadog Fluvial Options Appraisal | Gwynedd - Gwynedd | Defence | <100k | <250k | >5,000k | [7 empty] | <5,000k | Appraisal | Design | Construction | [7 empty] | TBC | TBC
Llyn Tegid Reservoir Safety Works | Gwynedd - Gwynedd | Maintenance | <100k | <100k | >5,000k | <5,000k | [6 empty] | >5,000k | Design | Maintenance | Maintenance | Maintenance
Valley | Isle of Anglesey - Sir Ynys Mon | Maintenance |  | <50k | [8 empty] | <50k |  | Maintenance
Ty Cwyfan Outfall removal | Isle of Anglesey - Sir Ynys Mon | Maintenance |  |  | <50k | [7 empty] | <50k |  |  | Maintenance
Malltraeth Tidal Doors Replacement | Isle of Anglesey - Sir Ynys Mon | Maintenance | <50k | [9 empty] | <50k | Maintenance
Llangefni | Isle of Anglesey - Sir Ynys Mon | Defence |  | <50k | <50k | <500k | [6 empty] | <500k |  | Appraisal | Design | Construction | [6 empty] | TBC | TBC
Afon Goch Amlwch | Isle of Anglesey - Sir Ynys Mon | Maintenance |  | <50k | <100k |  | <500k | [5 empty] | <1,000k |  | Appraisal | Design |  | Maintenance
Merthyr Tydfil - IPP/ New FAS | Merthyr Tydfil - Merthyr Tudful | Property Level Protection |  |  |  |  | <250k | [5 empty] | <250k |  |  |  |  | Other | [7 empty] | TBC
Troedyrhiw - New FAS [RB] | Merthyr Tydfil - Merthyr Tudful | Defence |  |  |  | <250k |  | <2,500k |  |  |  |  | <2,500k |  |  |  | Design |  | Construction |  |  |  |  | TBC | TBC
Monmouth | Monmouthshire - Sir Fynwy | Maintenance |  |  | <50k | [7 empty] | <50k |  |  | Maintenance
Usk Town | Monmouthshire - Sir Fynwy | Maintenance |  | <50k | [8 empty] | <50k |  | Maintenance
Redbrook Gauging Station Refurbishment | Monmouthshire - Sir Fynwy | Maintenance | <50k | <5k | [8 empty] | <50k | Maintenance | Maintenance
West Pill Outfall Improvments | Monmouthshire - Sir Fynwy | Maintenance | <50k | [9 empty] | <50k | Maintenance
Chepstow FAS - Gate Replacement | Monmouthshire - Sir Fynwy | Maintenance | <50k | [9 empty] | <50k | Maintenance
St Regis Sea Defence Repair | Monmouthshire - Sir Fynwy | Maintenance | <50k | [9 empty] | <50k | Maintenance
Peterstone Gout | Monmouthshire - Sir Fynwy | Maintenance |  | <50k | [8 empty] | <50k |  | Maintenance
Forge Rd & Watery Ln, Monmouth - IPP | Monmouthshire - Sir Fynwy | Property Level Protection | [5 empty] | <50k |  |  |  |  | <50k | [5 empty] | Other | [6 empty] | TBC
Glasbury Wall Left Bank Repairs | Monmouthshire - Sir Fynwy | Maintenance | <50k | [9 empty] | <50k | Maintenance
Sea Doors - Asset Replacement Study | Monmouthshire - Sir Fynwy | Maintenance | <50k | [9 empty] | <50k | Maintenance
Monmouth Flood Gates - Improvements | Monmouthshire - Sir Fynwy | Maintenance |  | <50k | [8 empty] | <50k |  | Maintenance
Portland Grounds Sea Defence Improvement | Monmouthshire - Sir Fynwy | Defence | <100k | [9 empty] | <100k | Completion | [9 empty] | 263 | 17
Monmouth - River Wye Left Bank | Monmouthshire - Sir Fynwy | Maintenance | [5 empty] | <250k |  |  |  |  | <250k | [5 empty] | Maintenance
Nedern Brook - River Restoration Project | Monmouthshire - Sir Fynwy | Maintenance |  |  |  |  | <500k | [5 empty] | <500k |  |  |  |  | Maintenance
Sudbrook/Chepstow - Sea Defence Improvements | Monmouthshire - Sir Fynwy | Maintenance | [5 empty] | <500k |  |  |  |  | <500k | [5 empty] | Maintenance
Pontardawe Floodbank | Neath Port Talbot - Castell-nedd Port Talbot | Maintenance | <50k | [9 empty] | <50k | Maintenance
Ffrwd Wyllt Fluvial Initial Assessment | Neath Port Talbot - Castell-nedd Port Talbot | Defence | <50k | [9 empty] | <50k | Appraisal
Marcroft Public Safety Risk Assessment | Neath Port Talbot - Castell-nedd Port Talbot | Maintenance | <50k | [9 empty] | <50k | Maintenance
Crynant Flood Risk Mapping Study | Neath Port Talbot - Castell-nedd Port Talbot | Modelling | <50k | [9 empty] | <50k | Study
Cwmgwrach Gabion Repairs and Channel Improvements | Neath Port Talbot - Castell-nedd Port Talbot | Maintenance | <50k | [9 empty] | <50k | Maintenance
Cwmafan | Neath Port Talbot - Castell-nedd Port Talbot | Maintenance | <50k | [9 empty] | <50k | Maintenance
Resolven Weir Refurbishment | Neath Port Talbot - Castell-nedd Port Talbot | Maintenance | <250k | [9 empty] | <250k | Maintenance
Cwm Clydach Dam Repairs | Neath Port Talbot - Castell-nedd Port Talbot | Maintenance | <250k | [9 empty] | <250k | Maintenance
Pontardawe and Cilmaengwyn Initial Assessment | Neath Port Talbot - Castell-nedd Port Talbot | Defence |  | <50k | <100k | [7 empty] | <250k |  | Appraisal | Appraisal
Cilfrew Weir Refurbishment | Neath Port Talbot - Castell-nedd Port Talbot | Maintenance | <50k | <250k | [8 empty] | <250k | Maintenance | Maintenance
Pontardawe Defences | Neath Port Talbot - Castell-nedd Port Talbot | Maintenance |  | <50k | <250k | [7 empty] | <500k |  | Design | Maintenance
Margam | Neath Port Talbot - Castell-nedd Port Talbot | Defence |  | <50k | <250k | <250k | [6 empty] | <500k |  | Design | Construction | Construction | [6 empty] | TBC | TBC
Stephenson Street, Liswerry | Newport - Casnewydd | Maintenance | <50k | [9 empty] | <50k | Maintenance
Chapel Reen Sea Door Replacement | Newport - Casnewydd | Maintenance | <50k | [9 empty] | <50k | Maintenance
Monks Ditch Sea Door Replacement | Newport - Casnewydd | Maintenance | <50k | [9 empty] | <50k | Maintenance
Undy Pumping Station Revetment Repairs | Newport - Casnewydd | Maintenance | <50k | [9 empty] | <50k | Maintenance
Back Ditch | Newport - Casnewydd | Maintenance |  |  |  | <50k | [6 empty] | <50k |  |  |  | Maintenance
Tredegar Park | Newport - Casnewydd | Maintenance |  |  | <50k | [7 empty] | <50k |  |  | Maintenance
Forge Mews, Bassaleg - Structural Assessment | Newport - Casnewydd | Maintenance |  |  |  | <50k | [6 empty] | <50k |  |  |  | Maintenance
Riverside Newport - 90s Wall [Structural Assessment] | Newport - Casnewydd | Maintenance |  |  |  |  | <50k | [5 empty] | <50k |  |  |  |  | Maintenance
Docksway Embankment and Deshoal | Newport - Casnewydd | Maintenance | <50k | [9 empty] | <50k | Maintenance
Home Farm, Caerleon - New FAS | Newport - Casnewydd | Defence |  | <100k | [8 empty] | <100k |  | Appraisal
Riverside Newport Flood Risk Management | Newport - Casnewydd | Defence | <100k | [9 empty] | <100k | Completion | [9 empty] | 373 | 47
Isca Road - Wall Repair | Newport - Casnewydd | Maintenance | <500k | <50k | [8 empty] | <500k | Construction | Completion | [8 empty] | 49 | 1
Tabbs Gout Sea Defence Improvements | Newport - Casnewydd | Defence | <500k | [9 empty] | <500k | Completion | [9 empty] | 570 | 180
Liswerry Pill - New FAS | Newport - Casnewydd | Defence |  | <50k | <100k |  | <2,500k | <2,500k |  |  |  |  | <5,000k |  | Appraisal | Design |  | Construction | Construction |  |  |  |  | TBC | TBC
Crindau Pill Flood Risk Management Improvements | Newport - Casnewydd | Defence | <5,000k | >5,000k | <5k | <50k | [6 empty] | >5,000k | Construction | Construction | Construction | Construction | [6 empty] | 549 | 118
NRW Civil Engineering Framework Agreement | Other | Other | <5k | [9 empty] | <5k | Other
ARC LITE Remote Control Boat | Other | Maintenance | <5k | [9 empty] | <5k | Other
FRA Scoping Assesment and Model Validation | Other | Modelling | <50k | [9 empty] | <50k | Study
Remote Monitoring by CCTV - MEICA | Other | Maintenance | <50k | [9 empty] | <50k | Maintenance
Hydrometry Bathymetry Equipment | Other | Other | <50k | [9 empty] | <50k | Other
NE Wales Tidal Defences Survey | Other | Modelling | <50k | <5k | <5k | <5k | <5k | [5 empty] | <50k | Study | Study | Study | Study | Study
FRM Transformation - Software Purchases | Other | ICT |  | <50k | <50k | [7 empty] | <50k |  | Other | Other
Coastal Outfall Maintenance Appraisal (SW ASM) | Other | Maintenance | <50k | [9 empty] | <50k | Maintenance
Third Party Assets Review (SW ASM) | Other | Maintenance | <50k | <5k | [8 empty] | <50k | Maintenance | Maintenance
Landscape Maintenance | Other | Maintenance | <50k | <5k | <5k | <5k | <5k | [5 empty] | <50k | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance
SW Access Areas | Other | Maintenance | <50k | [9 empty] | <50k | Maintenance
North Wales Culvert Inspection and Maintenance | Other | Maintenance | <50k | [9 empty] | <50k | Maintenance
Remote Monitoring of South East Sites by CCTV | Other | Maintenance | <50k | [9 empty] | <50k | Maintenance
South East Topographic Data Collection 16/17 | Other | Modelling | <50k | [9 empty] | <50k | Study
FRM Transformation - Software Support and Maintenance | Other | ICT | <50k | <50k | [8 empty] | <50k | Other | Other
FRM Transformation - Strategic Modelling Platform | Other | ICT | <50k | [9 empty] | <50k | Other
Contingency - Measures required following exercise | Other | Other |  | <50k | [8 empty] | <50k |  | Other
LIDAR for 2016/17 Flood Hazard Modelling | Other | Modelling | <50k | [9 empty] | <50k | Study
Northern Area Pumping Station Review | Other | Other | <50k | <50k | [8 empty] | <50k | Study | Study
Northern Area Topographic Survey Requirements | Other | Modelling | <50k | <50k | <50k | [7 empty] | <50k | Study | Study | Study
Review of IPP Candidate Sites (SE) | Other | Property Level Protection |  | <50k | [8 empty] | <50k |  | Other | [10 empty] | TBC
Clwyd Modelling Tidal Flood Risk | Other | Modelling |  |  |  |  | <50k | <50k |  |  |  |  | <100k |  |  |  |  | Study | Study
Public Safety Improvements 2016-17 | Other | Maintenance | <50k | [6 empty] | <50k | <50k | <50k | <100k | Maintenance | [6 empty] | Maintenance | Maintenance | Maintenance
FRM Transformation - FWD | Other | ICT | <100k | [9 empty] | <100k | Other
Culverts Moving Forward Project | Other | Maintenance |  | <50k | <50k | <50k | [6 empty] | <100k |  | Maintenance | Maintenance | Maintenance
Sea Door - CCTV Surveys | Other | Maintenance | [5 empty] | <50k | <50k | <50k |  |  | <100k | [5 empty] | Maintenance | Maintenance | Maintenance
River Ebbw Integrated Catchment Model | Other | Modelling | <100k | [9 empty] | <100k | Study
NHCP Land Investigations and Feasibility | Other | Biodiversity and Habitat Enhancement | <50k | <50k | <50k | <50k | [6 empty] | <100k | Other | Other | Other | Other
Culvert CCTV Survey Programme | Other | Maintenance | <50k | <50k | <50k | <50k | <50k | <50k | <50k | <50k | <50k | <50k | <250k | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance
NHCP Designated Site 6 | Other | Biodiversity and Habitat Enhancement |  | <100k | <50k | <250k | [6 empty] | <250k |  | Appraisal | Design | Construction | [10 empty] | TBC
Transport and Plant Hydrometry (Contribution) | Other | Vehicles | <50k | <50k | <50k | <50k | <50k | <50k | <50k | <50k | <50k | <50k | <250k | Other | Other | Other | Other | Other | Other | Other | Other | Other | Other
Replacement Flood Risk Asset Management System | Other | ICT | <250k | <100k | <100k | [7 empty] | <500k | Other | Other | Other
NHCP Designated Site 3 | Other | Biodiversity and Habitat Enhancement |  | <500k | [8 empty] | <500k |  | Construction | [12 empty] | TBC
NRW ICT FCRM Contribution | Other | ICT | <500k | [9 empty] | <500k | Other
Dee - Tidal Structure assessments / Designs | Other | Maintenance |  | <50k | <50k | <500k | [6 empty] | <500k |  | Maintenance | Maintenance | Maintenance
MEICA Asset Management Systems | Other | Maintenance |  | <50k | <50k | <50k | <50k | <50k | <50k | <50k | <50k | <50k | <500k |  | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance
Flood Forecasting Hydrometric Improvements | Other | Modelling | <50k | <50k | <50k | <50k | <50k | <50k | <50k | <50k | <50k | <50k | <500k | Study | Study | Study | Study | Study | Study | Study | Study | Study | Study
FRM Transformation - NFFS Replacement | Other | ICT | <500k | <500k | [8 empty] | <1,000k | Other | Other
Northern Area Mapping | Other | Modelling |  | <100k | <100k | <100k | <100k | <100k | <100k | <100k | <100k | <100k | <1,000k |  | Study | Study | Study | Study | Study | Study | Study | Study | Study
South East Area Mapping Projects | Other | Modelling |  | <100k | <100k | <100k | <100k | <100k | <100k | <100k | <100k | <100k | <1,000k |  | Study | Study | Study | Study | Study | Study | Study | Study | Study
South West Area Mapping projects | Other | Modelling |  | <100k | <100k | <100k | <100k | <100k | <100k | <100k | <100k | <100k | <1,000k |  | Study | Study | Study | Study | Study | Study | Study | Study | Study
Capital Maintenance Ops Delivery South East | Other | Maintenance |  | <250k | <250k | <250k | <250k | <250k | <250k | <250k | <250k | <250k | <2,500k |  | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance
Capital Maintenance Ops Delivery South West | Other | Maintenance |  | <250k | <250k | <250k | <250k | <250k | <250k | <250k | <250k | <250k | <2,500k |  | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance
Telemetry Wales 2020 (Telemetry Strategy) | Other | ICT | <100k | <250k | <500k | <500k | <500k | [5 empty] | <2,500k | Other | Other | Other | Other | Other
FRM Transformation - ICT Project Staff | Other | ICT | <2,500k | [9 empty] | <2,500k | Other
NHCP Designated Site 5 | Other | Biodiversity and Habitat Enhancement | <5k | <1,000k | <250k | <2,500k | [6 empty] | <2,500k | Design | Construction | Construction | Construction | [10 empty] | TBC
Capital Maintenance Ops Delivery North | Other | Maintenance |  | <500k | <500k | <500k | <500k | <500k | <500k | <500k | <500k | <500k | <2,500k |  | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance
NHCP Designated Site 2 | Other | Biodiversity and Habitat Enhancement | <50k | <250k | <250k | <1,000k | <2,500k | <2,500k |  |  | <500k |  | <5,000k | Appraisal | Design | Construction | Construction | Construction | Construction |  |  | Construction | [5 empty] | TBC
Wales FCRM Fleet Asset Replacement Programme | Other | Vehicles | <1,000k | <1,000k | <1,000k | <1,000k | <1,000k | <1,000k | <1,000k | <1,000k | <1,000k | <1,000k | >5,000k | Other | Other | Other | Other | Other | Other | Other | Other | Other | Other
NHCP Designated Site 4 | Other | Biodiversity and Habitat Enhancement |  |  |  | <2,500k | <5,000k |  | <5,000k | <2,500k | <500k |  | >5,000k |  |  |  | Design | Construction |  | Construction | Construction | Construction | [5 empty] | TBC
NHCP Designated Site 7 | Other | Biodiversity and Habitat Enhancement | <500k |  |  | <2,500k | <2,500k | <5,000k | >5,000k | <1,000k | <500k |  | >5,000k | Appraisal |  |  | Design | Construction | Construction | Construction | Construction | Construction | [5 empty] | TBC
Wales FRM Capital Sals (EAW) | Other | Other | <2,500k | <2,500k | <2,500k | <2,500k | <2,500k | <2,500k | <2,500k | <2,500k | <2,500k | <2,500k | >5,000k | Other | Other | Other | Other | Other | Other | Other | Other | Other | Other
NHCP Designated Site 1 | Other | Biodiversity and Habitat Enhancement |  |  | <100k | <250k |  | <1,000k |  |  |  | >5,000k | >5,000k |  |  | Appraisal | Design |  | Construction |  |  |  | Construction |  |  |  |  | TBC
Prendergast Mill Bank Repair | Pembrokeshire - Sir Benfro | Maintenance | <5k | [9 empty] | <5k | Maintenance
Cilrhedyn Bridge | Pembrokeshire - Sir Benfro | Maintenance | <50k | [9 empty] | <50k | Maintenance
Cartlett Brook Flood Wall | Pembrokeshire - Sir Benfro | Maintenance | <50k | [9 empty] | <50k | Maintenance
Pont y Cerbyd Access Improvements | Pembrokeshire - Sir Benfro | Maintenance | <50k | [9 empty] | <50k | Maintenance
Haverfordwest Ops | Pembrokeshire - Sir Benfro | Maintenance |  | <5k | <50k | [7 empty] | <50k |  | Maintenance | Maintenance
Pont y Cerbyd Reservoir Section 10 | Pembrokeshire - Sir Benfro | Maintenance | <50k | [9 empty] | <50k | Maintenance
Tenby Buoy Assessment | Pembrokeshire - Sir Benfro | Maintenance | <100k | [9 empty] | <100k | Maintenance
Ritec Culvert Improvements | Pembrokeshire - Sir Benfro | Maintenance |  | <100k | [8 empty] | <100k |  | Maintenance
Haverfordwest | Pembrokeshire - Sir Benfro | Defence |  | <50k | <250k | <250k | [6 empty] | <500k |  | Appraisal | Design | Construction | [6 empty] | TBC | TBC
Pan Teg Weir | Powys - Powys | Maintenance | <5k | [9 empty] | <5k | Maintenance
Welshpool | Powys - Powys | Maintenance |  |  |  | <50k | [6 empty] | <50k |  |  |  | Maintenance
Ystradgynlais Flood Risk Management | Powys - Powys | Defence | <50k | <5k | [8 empty] | <50k | Completion | Completion | [8 empty] | 228 | 16
Llanwrytyd Wells | Powys - Powys | Maintenance |  |  | <50k | [7 empty] | <50k |  |  | Maintenance
Llanwrytyd Wells | Powys - Powys | Maintenance |  |  | <50k | [7 empty] | <50k |  |  | Maintenance
Caersws RB - IPP | Powys - Powys | Property Level Protection |  | <50k | [8 empty] | <50k |  | Other | [10 empty] | TBC
Brecon - Structural Assessment | Powys - Powys | Maintenance |  |  | <50k | [7 empty] | <50k |  |  | Maintenance
Glasbury - Structural Assessment | Powys - Powys | Maintenance |  |  |  |  | <50k | [5 empty] | <50k |  |  |  |  | Maintenance
Brecon | Powys - Powys | Maintenance |  |  |  | <50k | [6 empty] | <50k |  |  |  | Maintenance
Llanidloes | Powys - Powys | Maintenance |  |  |  |  | <50k | [5 empty] | <50k |  |  |  |  | Maintenance
Newtown - Structural Assessment | Powys - Powys | Maintenance |  |  |  |  | <50k | <50k |  |  |  |  | <100k |  |  |  |  | Maintenance | Maintenance
Cilmery Gauiging Station Refurbishment | Powys - Powys | Maintenance | <50k | <50k | [8 empty] | <100k | Maintenance | Maintenance
Haimwood - Improvements/ Repairs | Powys - Powys | Maintenance | <100k | [9 empty] | <100k | Maintenance
Esgair Carnau - Bank Protection | Powys - Powys | Maintenance | <50k | <50k | <100k | [7 empty] | <250k | Design | Maintenance | Maintenance
Aberdare | Rhondda Cynon Taf - Rhondda Cynon Taf | Maintenance |  |  |  |  | <5k | [5 empty] | <5k |  |  |  |  | Maintenance
Aberdare Culvert | Rhondda Cynon Taf - Rhondda Cynon Taf | Maintenance |  | <50k | [8 empty] | <50k |  | Maintenance
Porth/Hopkinstown | Rhondda Cynon Taf - Rhondda Cynon Taf | Maintenance |  |  |  |  | <50k | [5 empty] | <50k |  |  |  |  | Maintenance
Treforest | Rhondda Cynon Taf - Rhondda Cynon Taf | Maintenance |  | <50k | [8 empty] | <50k |  | Maintenance
Nant Aman Culvert Screen | Rhondda Cynon Taf - Rhondda Cynon Taf | Maintenance |  |  |  | <50k | [6 empty] | <50k |  |  |  | Maintenance
Gelli - Revenue Works Identified in Structural Assessment | Rhondda Cynon Taf - Rhondda Cynon Taf | Maintenance |  | <50k | [8 empty] | <50k |  | Maintenance
Rhondda Confluence | Rhondda Cynon Taf - Rhondda Cynon Taf | Maintenance |  |  |  | <50k | [6 empty] | <50k |  |  |  | Maintenance
Pontyclun | Rhondda Cynon Taf - Rhondda Cynon Taf | Maintenance |  |  |  |  | <50k | [5 empty] | <50k |  |  |  |  | Maintenance
Britannia Porth - IPP | Rhondda Cynon Taf - Rhondda Cynon Taf | Property Level Protection |  | <50k | [8 empty] | <50k |  | Other | [10 empty] | TBC
Taffs Well - Pumping Solution | Rhondda Cynon Taf - Rhondda Cynon Taf | Maintenance |  | <50k | [8 empty] | <50k |  | Maintenance
Ynysddu - Structural Assessment | Rhondda Cynon Taf - Rhondda Cynon Taf | Maintenance |  |  |  |  | <50k | [5 empty] | <50k |  |  |  |  | Maintenance
Treforest Embankment Reprofile and Repairs | Rhondda Cynon Taf - Rhondda Cynon Taf | Maintenance | <50k | [9 empty] | <50k | Maintenance
Trehafod | Rhondda Cynon Taf - Rhondda Cynon Taf | Maintenance |  |  |  |  | <50k | [5 empty] | <50k |  |  |  |  | Maintenance
Hawthorn | Rhondda Cynon Taf - Rhondda Cynon Taf | Maintenance |  | <50k | [8 empty] | <50k |  | Maintenance
Treforest Ind Est - Structural Assessment | Rhondda Cynon Taf - Rhondda Cynon Taf | Maintenance |  |  | <50k | [7 empty] | <50k |  |  | Maintenance
Forge Row & Farm Rd, Aberaman - IPP | Rhondda Cynon Taf - Rhondda Cynon Taf | Property Level Protection |  |  |  |  | <50k | [5 empty] | <50k |  |  |  |  | Other | [7 empty] | TBC
Rhondda Walls- Structural Assessment | Rhondda Cynon Taf - Rhondda Cynon Taf | Maintenance | <50k | [9 empty] | <50k | Maintenance
Sion Street Pontypridd - Wall Refurbishment | Rhondda Cynon Taf - Rhondda Cynon Taf | Maintenance | <50k | [9 empty] | <50k | Maintenance
Hirwaun - New FAS | Rhondda Cynon Taf - Rhondda Cynon Taf | Defence |  |  | <100k | [7 empty] | <100k |  |  | Construction
Porth - Improve FAS | Rhondda Cynon Taf - Rhondda Cynon Taf | Maintenance |  |  |  |  | <100k | [5 empty] | <100k |  |  |  |  | Maintenance
Glyntaff - IPP | Rhondda Cynon Taf - Rhondda Cynon Taf | Property Level Protection |  |  |  |  | <250k | [5 empty] | <250k |  |  |  |  | Other | [7 empty] | TBC
Treforest Flood Alleviation Scheme - Wall Repair | Rhondda Cynon Taf - Rhondda Cynon Taf | Maintenance |  | <250k | [8 empty] | <250k |  | Maintenance
Eileen Place, Tynewydd | Rhondda Cynon Taf - Rhondda Cynon Taf | Defence | [5 empty] | <500k |  |  |  |  | <500k | [5 empty] | Construction
Treherbert Park & David Street - Improve FAS | Rhondda Cynon Taf - Rhondda Cynon Taf | Maintenance | [5 empty] | <500k |  |  |  |  | <500k | [5 empty] | Maintenance
Treforest/Hawthorn | Rhondda Cynon Taf - Rhondda Cynon Taf | Defence |  |  |  | <500k | <5,000k | [5 empty] | <5,000k |  |  |  | Design | Construction | [5 empty] | TBC | TBC
Gowerton Headwall and Floodbank Repair | Swansea - Abertawe | Maintenance | <5k | [9 empty] | <5k | Maintenance
Cwm Ivy Land Purchase | Swansea - Abertawe | Biodiversity and Habitat Enhancement | <5k | [9 empty] | <5k | Other
Ynystanglws Bank Wall Improvements | Swansea - Abertawe | Maintenance | <50k | [9 empty] | <50k | Maintenance
Gorseinon FAS | Swansea - Abertawe | Defence |  | <50k | [8 empty] | <50k |  | Construction
Swansea Valley Flood Risk Mapping Studies | Swansea - Abertawe | Modelling | <50k | [9 empty] | <50k | Study
Ynystawe Park Floodbank Repair | Swansea - Abertawe | Maintenance | <50k | [9 empty] | <50k | Maintenance
Lower Swansea Vale Flood Risk Management | Swansea - Abertawe | Defence | <50k | <50k | <5k | [7 empty] | <100k | Completion | Completion | Completion | [7 empty] | 6 | 284
Cwm Ivy Marsh Managed Realignment | Swansea - Abertawe | Biodiversity and Habitat Enhancement | <50k | <50k | <50k | <50k | <50k | [5 empty] | <100k | Completion | Completion | Completion | Completion | Completion
Penclawdd Flood Risk Management | Swansea - Abertawe | Defence | <250k | [9 empty] | <250k | Construction | [9 empty] | 127 | 15
Llansamlet Initial Assessment | Swansea - Abertawe | Defence |  |  | <50k | <50k | <250k | [5 empty] | <250k |  |  | Appraisal | Design | Construction
Pontarddulais Flood Risk Management | Swansea - Abertawe | Defence | <1,000k | <250k | [8 empty] | <2,500k | Construction | Construction | [8 empty] | 224 | 22
Swansea Tidal Defences | Swansea - Abertawe | Defence |  | <50k | <50k | <5,000k | [6 empty] | <5,000k |  | Study | Design | Construction | [6 empty] | TBC | TBC
Sportsman's Rest, Peterstone Super Ely - IPP | The Vale of Glamorgan - Bro Morgannwg | Property Level Protection |  | <50k | [8 empty] | <50k |  | Other | [10 empty] | TBC
Cowbridge FAS - Replacement Sleepers and Toe Drain | The Vale of Glamorgan - Bro Morgannwg | Maintenance | <50k | [9 empty] | <50k | Maintenance
River Walk & River Way, Llandough - IPP | The Vale of Glamorgan - Bro Morgannwg | Property Level Protection |  | <50k | [8 empty] | <50k |  | Other | [10 empty] | TBC
St Cadoc's Ave, Dinas Powis - IPP | The Vale of Glamorgan - Bro Morgannwg | Property Level Protection |  | <50k | [8 empty] | <50k |  | Other | [10 empty] | TBC
Lawrenny Avenue - New Embankment | The Vale of Glamorgan - Bro Morgannwg | Defence |  |  | <100k | [7 empty] | <100k |  |  | Construction
Aberthin - IPP | The Vale of Glamorgan - Bro Morgannwg | Property Level Protection | [5 empty] | <100k |  |  |  |  | <100k | [5 empty] | Other | [6 empty] | TBC
Leckwith Bridge Ind Est | The Vale of Glamorgan - Bro Morgannwg | Defence |  |  |  |  | <250k | [5 empty] | <250k |  |  |  |  | Construction
Contribution to Coldbrook FAS | The Vale of Glamorgan - Bro Morgannwg | Defence | <500k | [9 empty] | <500k | Construction
Cadoxton Initial Assessment | The Vale of Glamorgan - Bro Morgannwg | Defence |  | <50k | <250k | <250k | [6 empty] | <500k |  | Appraisal | Design | Construction
River Cadaxton Improvements | The Vale of Glamorgan - Bro Morgannwg | Maintenance | <50k | <100k | <250k | <2,500k | <2,500k | [5 empty] | <5,000k | Appraisal | Design | Maintenance | Maintenance | Maintenance
Ponthir - Structural Assessment | Torfaen - Tor-faen | Maintenance |  |  | <50k | [7 empty] | <50k |  |  | Maintenance
Llanyrafon, Cwmbran - Improve FAS | Torfaen - Tor-faen | Maintenance |  | <50k | [8 empty] | <50k |  | Maintenance
Chapel Lane, Cwmbran - New FAS | Torfaen - Tor-faen | Defence |  |  |  |  | <100k | [5 empty] | <100k |  |  |  |  | Construction
Manley Hall Gauging Station Refurbishment | Wrexham - Wrecsam | Maintenance | <50k | [9 empty] | <50k | Maintenance